## Instructions
This calculator is an expanded version of the ES Calculator. The Milestone SV(t) Forecast Calculator provides the forecast for schedule variance, F-SV(t), with respect to a
given project schedule milestone. As well, TSPI values, TSPIM, are computed using the milestone duration and its allowable slippage. Effective application of the calculator
requires the creation of the performance measurement baseline for the milestone of interest. The terms with the subscript "M" identify their association with the baseline.
Just as for the ES Calculator, enter data to the EVM and PVM columns of the Milestone Forecast sheet. Note that row 3 is the 1st data entry. Before each use clear all data
in columns A and B below row 2. As well, clear the other entries in tan colored cells in columns, N, O, Q, and R. To insure correctly calculated values, load the entire baseline
(periodic values of PVM) into column B. Enter BACM in the PVM column one time only. Entering BACM more than once will cause the message, ERROR, to appear instead of
computed values for ESM, SPI(t)M, SV(t)M, F-SV(t), and TSPIM, as well as their respective periodic values.
Next, enter the date of the period which includes the milestone to be monitored in the Status Date column corresponding to the appropriate Period number. Copy the date and
paste to cell O3 beneath the Milestone heading. Enter the actual milestone date in the same column below the Milstn Date heading. The allowable milestone slippage in days
is entered to cell O7, beneath the heading Milstn Slack (da). Choose the performance factor to use in the calculation, by entering "S" or "V." Entering "S," selects the current
SPI(t)M value. By using "V," the forecast is the current SV(t)M converted to days. It assumes the remaining portion of planned work will be performed as planned, i.e., SPI(t)M
equal to 1.00. Lastly, enter the duration unit of the Period; i.e., Month (M), Bi-Weekly (B), or Weekly (W). The number shown for F-SV(t) is taken as a positive variance (ahead
of schedule) when it is unsigned. When the number is negative, improvement is needed to achieve the milestone. If the corresponding TSPIM value is less than or equal to 1.10,
recovery and achievement of the milestone is possible.
The calculator is capable of handling up to 50 periodic entries. When the application has more entries than 50, extending the calculator will be required, but should not be overly
difficult.
It is recommended to use the Example Data & Results worksheet to become familiar with the spreadsheet and its terminology.

## Milestone Forecast
EVM | PVM | # Pc=>Sc | Numerator | Denominator | InterpVal | ESM | ESp | SPI(t)p | SPI(t)M | SV(t)p | SV(t)M | Period | Status Date | Milestone | F-SV(t) | Perf-Fac | Conv-Days | TSPIM
0 | 0 | [11 empty] | mo/da/yr |  | days | S or V | M, B, or W
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 1 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 2 |  | Milstn Date | F-SV(t) |  | Conv-Days | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 3 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 4 |  | Milstn Duration | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 5 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 6 |  | Milstn Slack (da) | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 7 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 8 |  | Status Period | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 9 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 10 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 11 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 12 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 13 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 14 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 15 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 16 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 17 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 18 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 19 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 20 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 21 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 22 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 23 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 24 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 25 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 26 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 27 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 28 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 29 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 30 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 31 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 32 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 33 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 34 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 35 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 36 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 37 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 38 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 39 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 40 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 41 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 42 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 43 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 44 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 45 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 46 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 47 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 48 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 49 |  |  | F-SV(t) |  |  | TSPIm
|  | Pc=>Sc | NUM | DENOM | InterpVal | ESm | ESp | SPI(t)p | SPI(t)m | SV(t)p | SV(t)m | 50 |  |  | F-SV(t) |  |  | TSPIm
BAC Count | 0

## Example Data & Results
EVM | PVM | ESM | SPI(t)M | Period | Status Date | Milestone | F-SV(t) | Perf-Fac | Conv-Days | TSPIM
0 | 0 |  |  |  | mo/da/yr |  | days | S or V | M, B, or W
87 | 93 | 0.93548 | 0.93548 | 1 |  | 2017-06-01 | -37.4524 | S | M | 1.0018 | Notes:
358 | 644 | 1.4809 | 0.74047 | 2 |  | Milstn Date | -194.4193 |  | Conv-Days | 1.0297
876 | 975 | 2.7009 | 0.9003 | 3 |  | 2017-06-11 | -60.7432 |  | 30.42 | 1.0173 | Status Date is the first day after the close of a performance period. The date entered designates the period in which the milestone occurs.
1135 | 1275 | 3.5333 | 0.88333 | 4 |  | Milstn Duration | -72.64 |  |  | 1.0302
1534 | 1739 | 4.5582 | 0.91164 | 5 |  | 18.3287 | -53.0425 |  |  | 1.0306 | Milstn Date is the date designated to achieve a portion of the project. It is within the period of performance whose beginning is designated by
2178 | 2292 | 5.7939 | 0.96564 | 6 |  | Milstn Slack (da) | -18.8383 |  |  | 1.014 |  | the Status Date entry.
2798 | 3331 | 6.487 | 0.92672 | 7 |  | 1 | -43.0919 |  |  | 1.0423
3680 | 3869 | 7.6487 | 0.95609 | 8 |  | Status Period | -24.6085 |  |  | 1.0307 | Milstn Slack is the number of days after the Milstn Date for which completion of the milestone is regarded as acceptable. If it is desired to
4590 | 4612 | 8.9704 | 0.99671 | 9 |  | 18 | -0.84041 |  |  | 0.99965 |  | focus on the Milstn Date leave the Milstn Slack entry blank.
5513 | 5527 | 9.9847 | 0.99847 | 10 |  |  | 0.1456 |  |  | 0.9979
6480 | 6575 | 10.9094 | 0.99176 | 11 |  |  | -3.6329 |  |  | 1.0078 | The negative values shown in column F-SV(t) indicate the number of days of improvement needed between the current Period and the
7289 | 7991 | 11.5042 | 0.95869 | 12 |  |  | -23.0274 |  |  | 1.0728 |  | Milstn Date plus slack.
8855 | 9193 | 12.7188 | 0.97837 | 13 |  |  | -11.327 |  |  | 1.0463
9993 | 10831 | 13.4884 | 0.96346 | 14 |  |  | -20.1476 |  |  | 1.1098 | TSPIM values > 1.10 are shown in Red, indicating recovery to the milestone date including slack, when entered, is not likely when EScum >
| 12946 | ESm | SPI(t)m | 15 |  |  | F-SV(t) |  |  | TSPIm |  | 0.15 of project duration.
| 14295 | ESm | SPI(t)m | 16 |  |  | F-SV(t) |  |  | TSPIm
| 16051 | ESm | SPI(t)m | 17 |  |  | F-SV(t) |  |  | TSPIm
| 17808 | ESm | SPI(t)m | 18 | 2017-06-01 |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 19 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 20 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 21 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 22 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 23 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 24 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 25 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 26 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 27 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 28 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 29 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 30 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 31 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 32 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 33 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 34 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 35 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 36 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 37 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 38 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 39 |  |  | F-SV(t) |  |  | TSPIm
|  | ESm | SPI(t)m | 40 |  |  | F-SV(t) |  |  | TSPIm