## Instructions
Enter EVcum and PVcum into columns A and B of the EScalc sheet.
Note that row 3 is the 1st data entry. Before each use clear all data
in columns A and B below row 2. To insure correctly calculated values, load
the entire baseline (periodic values of PVcum) into column B. Enter PV =
BAC one time only. Entering PV = BAC for time periods past the planned
duration (PD) will cause the message, ERROR, to appear instead of
computed values for ES, SPI(t), and SV(t).
Computed values for SPI(t)mo, SPI(t)cum, SV(t)mo, and SV(t)cum are
displayed in columns I, J, L, and M, respectively. The cumulative actual
time (AT) is shown in column K.
The calculator is capable of handling up to 50 periodic entries. If the
application has more entries than 50, simply extend columns C through
M to the number needed. The range of the COUNTIF function in column C
will need to be extended to include the last PV entry. To retain multiple BAC
entry checking, requires several changes in columns B, G, H, I, J, L, and M.

## EScalc
EVcum | PVcum | # Pc=>Sc | Numerator | Denominator | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
0 | 0 | [8 empty] | 0
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
BAC Count | 0

## Example Data
EVcum | PVcum |  | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum
93 | 93 | Compare your results obtained from using | 1 | 1 | 1 | 0 | 0
644 | 644 | this data to their corresponding values in | 1 | 1 | 2 | 0 | 0
1710 | 975 | columns I, J, L, M. | 2.9375 | 1.6458 | 3 | 1.9375 | 1.9375
2397 | 1275 |  | 1.1636 | 1.5253 | 4 | 0.16356 | 2.1011
3060 | 1739 |  | 0.63811 | 1.3478 | 5 | -0.36189 | 1.7392
3923 | 2292 |  | 1.3335 | 1.3454 | 6 | 0.33351 | 2.0727
4722 | 3331 |  | 1.0475 | 1.3029 | 7 | 0.04754 | 2.1202
5743 | 3869 |  | 1.0859 | 1.2758 | 8 | 0.085888 | 2.2061
7369 | 4612 |  | 1.3546 | 1.2845 | 9 | 0.35463 | 2.5607
9005 | 5527 |  | 1.2829 | 1.2844 | 10 | 0.28286 | 2.8436
10850 | 6575 |  | 1.1654 | 1.2735 | 11 | 0.16539 | 3.009
12218 | 7991 |  | 0.64681 | 1.2213 | 12 | -0.35319 | 2.6558
13921 | 9193 |  | 1.067 | 1.2094 | 13 | 0.066966 | 2.7228
15417 | 10831 |  | 0.91619 | 1.1885 | 14 | -0.083805 | 2.639
18170 | 12946 |  | 1.5559 | 1.213 | 15 | 0.55588 | 3.1948
20022 | 14295 |  | 1.0406 | 1.2022 | 16 | 0.040617 | 3.2354
21936 | 16051 |  | 1.2209 | 1.2033 | 17 | 0.2209 | 3.4564
24418 | 17808 |  | 1.32 | 1.2098 | 18 | 0.31995 | 3.7763
26186 | 19666 |  | 1.1374 | 1.206 | 19 | 0.13741 | 3.9137
27972 | 21178 |  | 1.2672 | 1.209 | 20 | 0.2672 | 4.1809
29397 | 22839 |  | 1.0588 | 1.2019 | 21 | 0.058758 | 4.2397
30899 | 24873 |  | 1.155 | 1.1998 | 22 | 0.15495 | 4.3946
26310
27720
29113
30298
31821