## Instructions
Enter BCWPcum and BCWScum into columns A and B of the EScalc sheet.
Note that row 11 is the 1st data entry. Before each use clear all data
in columns A and B below row 10. To insure correctly calculated values, load
the entire baseline (periodic values of BCWScum) into column B.
Enter plan start and completion dates into cells C1 and G1, respectively.
Enter actual completion date into cell C5 when project completes.
Enter 1st and last days into cells C2, G2, and C6, as appropriate. Enter BAC.
Computed values for SPI(t)mo, SPI(t)cum, SV(t)mo, and SV(t)cum are
displayed in columns J, K, N, and O, respectively. The cumulative actual
time (AT) is shown in column M.
The calculator is capable of handling up to 50 periodic entries. If the
application has more entries than 50, simply extend columns C through
O to the number needed. The range of the COUNTIF function in column C will
need to be extended to include the last BCWS entry.

## EScalc
Plan Start Date = |  |  |  | Plan Compl Date =
1st Day Next Mo = |  |  |  | Last Day Previous Mo =
1st mo Fraction (Pln) = |  | 0 |  | Last mo Fraction (Pln) = |  | 0
Actual Compl Date = |  |  |  | BAC
Last Day Previous Mo =
Last mo Fraction (Act) = |  | 0
EVcum | PVcum | # Pc=>Sc | E-Count | Numerator | Denominator | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum
|  | Pc=>Sc | E-Count | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | A-Count | AT | SV(t)mo | SV(t)cum

## Example Data
BCWPcum | BCWScum |  |  |  | SPI(t)mo | SPI(t)cum | A-Count | SV(t)mo | SV(t)cum
75 | 93 | Compare your results obtained from using |  |  | 0.80645 | 0.80645 | 1 | -0.10968 | -0.10968
625 | 644 | this data to their corrsponding values in |  |  | 1.0752 | 0.97799 | 2 | 0.075195 | -0.034483
1710 | 975 | columns I, J, L, M. |  |  | 2.972 | 1.7549 | 3 | 1.972 | 1.9375
2397 | 1275 |  |  |  | 1.1636 | 1.5891 | 4 | 0.16356 | 2.1011
3060 | 1739 | Plan Start Date = |  | 2000-11-14 | 0.63811 | 1.3808 | 5 | -0.36189 | 1.7392
3923 | 2292 | Plan Completion Date = |  | 2003-05-15 | 1.3335 | 1.3723 | 6 | 0.33351 | 2.0727
4722 | 3331 | Actual Completion Date = |  | 2003-01-03 | 1.0475 | 1.3229 | 7 | 0.04754 | 2.1202
5743 | 3869 |  | BAC = | 31821 | 1.0859 | 1.2916 | 8 | 0.085888 | 2.2061
7369 | 4612 |  |  |  | 1.3546 | 1.2989 | 9 | 0.35463 | 2.5607
9005 | 5527 |  |  |  | 1.2829 | 1.2972 | 10 | 0.28286 | 2.8436
10850 | 6575 |  |  |  | 1.1654 | 1.2848 | 11 | 0.16539 | 3.009
12218 | 7991 |  |  |  | 0.64681 | 1.2296 | 12 | -0.35319 | 2.6558
13921 | 9193 |  |  |  | 1.067 | 1.2167 | 13 | 0.066966 | 2.7228
15417 | 10831 |  |  |  | 0.91619 | 1.1945 | 14 | -0.083805 | 2.639
18170 | 12946 |  |  |  | 1.5559 | 1.2193 | 15 | 0.55588 | 3.1948
20022 | 14295 |  |  |  | 1.0406 | 1.2078 | 16 | 0.040617 | 3.2354
21936 | 16051 |  |  |  | 1.2209 | 1.2086 | 17 | 0.2209 | 3.4564
24418 | 17808 |  |  |  | 1.32 | 1.215 | 18 | 0.31995 | 3.7763
26186 | 19666 |  |  |  | 1.1374 | 1.2108 | 19 | 0.13741 | 3.9137
27972 | 21178 |  |  |  | 1.2672 | 1.2137 | 20 | 0.2672 | 4.1809
29397 | 22839 |  |  |  | 1.0588 | 1.2061 | 21 | 0.058758 | 4.2397
30899 | 24873 |  |  |  | 1.155 | 1.2038 | 22 | 0.15495 | 4.3946
31821 | 26310 |  |  |  | 1.0538 | 1.2031 | 23 | 0.0053841 | 4.4
27720
29113
30298
31821