## Special Case Instructions
ES Special Case Instructions
Step 1. | Clear the Data Entry sheet at columns A and B beginning at row #4.
Step 2. | Enter the planned PV into Data Entry sheet beneath column heading "iPVcum." Planned periods of down time are
entered as "XX."
Step 3. | Enter the accrued EV into Data Entry sheet as it is recorded beneath column heading "iEVcum." For periods of stop
work enter "XX."
Step 4. | When entry has been completed to the iEVcum and iPVcum columns on the Data Entry sheet, two other arrangements
of the data will be shown on the Data Conv sheet. The EScalc and ESnxcalc arrangements are used in the special case
calculations. The data depicted for EScalc will contain repeated data due to the stop work and down time periods. For the
ESnx arrangement all stop work and down time entries are removed. The EScalc data arrangement is used to generate
the forecasts made from using the basic ES calculator. These forecasts are used for comparison to the special forecast
calculations.
Step 5. | The EScalc and EScalc Special worksheets perform all of the calculations. These worksheets feed the output sheets,
Special Forecast and Special Indicators. Consolidated forecast results appear on the Special Forecast sheet. The results
are portrayed numerically and graphically. The scale on the graph and data portrayed will likely require adjusting for each
application. To insure all data are shown properly on the graph, click the plot area. Observe the data included in the table
area of the worksheet and move the lower blue line to include the last line of numbers.
Step 6. | When forecast completion dates are desired, enter the Start Date on the Data Entry sheet at cell E4 in the format
Month/Day/Year; otherwise clear cell E4. When the Start Date is entered, the status period length (Month, Bi-Week,
Week) requires entry at cell E8.
Step 7. | The Special Indicators sheet contains the values for the time-based schedule performance index and the schedule
variance for the down time or stop work conditions. The special indicators are prefaced with "i," to avoid confusion.
Application Notes
In general, this spreadsheet is intended for application to projects having interrupted performance. The spreadsheet
accommodates up to 200 periods of performance. If more than 200 periods are needed, the worksheets will require
modification, including the two hidden sheets, Data Conv and EScalc.
The "special cases" to which this spreadsheet specifically applies are the following:
| 1) | The PMB includes planned "down" periods; i.e., periods which have no planned PV. As an example,
employees are planned to be shifted to other work for six weeks due to a scheduled facility repair.
| 2) | Management makes a decision during execution to stop project activity for a period until some condition is
resolved. No EV is accrued during the stop work periods.
| 3) | The PMB includes planned "down" periods, but the work conditions are such that the employees perform
work and accrue EV.
The spreadsheet is capable of accommodating combinations of the above described special cases. When the
spreadsheet is used for determining longest path (LP), the sheet providing ES(L) will be needed. For LP application, the
project planned duration (PD) must be entered to the Data Entry sheet, cell E16. When applied for LP, the data entry
must be made for each path. The computed values are then entered to tables like those shown on Longest Path sheet.
Selection is made for the LP forecast and its corresponding ES-LP, as shown in the bottom table. The normalized values
from the Normalized Measures sheet are the input measures to the Statistical Forecasting Calculator when there are
performance interruptions,
When work is performed, yet EV is not earned, the entry to be made to the Data Entry sheet is zero and not
XX. This situation is not a "special case." The EV entry in this circumstance should indicate no progress
advancement; i.e., EVp = 0.0.
Five data sets are provided to assist with learning to use the special case calculator. Each of the data sets has a graph
of the results. The graphs are provided for assurance comparison during experimentation with the calculator and the data.

## Data Entry
Data Entry
iEVcum | iPVcum
Start Date
Enter =>
Status Period Length (Days)
|  | Enter => | M
|  | Month | M | 30.42
|  | Bi-Week | B | 14
|  | Week | W | 7
|  | Multipier | 30.42
Project Planned Duration
Enter =>

## Data Conv (hidden)
Data Entry |  | ES Calc |  | ESnx Calc |  | Position
iEVcum | iPVcum | EVcum | PVcum | EVnxcum | PVnxcum | EVsp | PVsp | Count
0 | 0 | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## EScalc (hidden)
EVcum | PVcum | # Pc=>Sc | Numerator | Denominator | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t) | Comp Date | Multipier | 30.42
0 | 0 | [8 empty] | 0 |  |  | 0 | Start Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)es | Comp Date

## EScalc Special
EVnxcum | PVnxcum | # Pc=>Sc | Numerator | Denominator | InterpVal | ESnxcum | ESnxper | SPI(t)nxper | SPI(t)nxcum | AT | SV(t)nxper | SV(t)nxcum | IEAC(t)nx | Comp Date | iEVcum | iPVcum | Period | IEAC(t)sp | Comp Date | Count iEV XX | Count iPV XX | IEAC(t)sp2 | DT Count | Normalized ES
0 | 0 | [8 empty] | 0 |  |  |  |  | 0 | 0
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESper | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | IEAC(t)nx | Comp Date |  |  | Period | IEAC(t)sp | Comp Date | 0 | 0 | IEAC(t)sp | DT Count
[14 empty] | Start Date | EVp=0 Periods | PVp=0 Periods |  | Multipier | 30.42
[14 empty] | Start Date | 0 | 0
[15 empty] | EV Periods | PV Periods
[15 empty] | 0 | 0
[15 empty] | Actual Periods | Total Plan Dur
[15 empty] | 0 | 0

## Special Forecast
Period | IEAC(t)sp | IEAC(t) | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date
Period | IEAC(t)sp | IEAC(t)es | Plan Dur | Actual Dur | Comp Date

## Special Indicators
EVMnx Data |  | ESnx Indicators | [6 empty] | iEVM Data |  |  | Special Indicators
EVnxcum | PVnxcum | SPI(t)nxper | SPI(t)nxcum | AT | SV(t)nxper | SV(t)nxcum | Count iEV XX | Count iPV XX | iEVcum | iPVcum | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | iSV(t)cum | iSV(t)cum
0 | 0 |  |  | 0 |  |  |  |  | 0 | 0 |  |  |  |  | w/o Down time | + Down Time
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
|  | SPI(t)per | SPI(t)cum | AT | SV(t)per | SV(t)cum | Count iEV XX | Count iPV XX |  |  | Period | iSPI(t)per | iSPI(t)cum | iSV(t)per | wo DT | iSV(t)cum
[9 empty] | EVp=0 Periods | PVp=0 Periods
[9 empty] | 0 | 0
[9 empty] | EV Periods | PV Periods
[9 empty] | 0 | 0
[9 empty] | Actual Periods | Total Plan Dur
[9 empty] | 0 | 0

## Normalized Measures
Period | iEVcum | iPVcum | Normalized EV | Normalized PV | Normalized ES | EV XX Pos | EV SecQ | EV XX Nr | EV Increment | Calc EV Norm | PV XX Pos | PV SecQ | PV XX Nr | PV Increment | Calc PV Norm | Period | iEVcum | iPVcum | Normalized EV | Normalized PV | Normalized ES
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 1 | 93 | 93 | 93 | 93 | 1
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 2 | 644 | 644 | 644 | 644 | 2
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 3 | 975 | 1710 | 975 | 1710 | 2.392
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 4 | 1275 | 2397 | 1275 | 2397 | 2.7345
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 5 | 1739 | 3060 | 1739 | 3060 | 3.2296
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 6 | XX | 3923 | 1923.3333 | 3923 | 3.7849
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 7 | XX | 4722 | 2107.6667 | 4722 | 4.3149
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 8 | 2292 | 5743 | 2292 | 5743 | 5.1588
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 9 | 3331 | 7369 | 3331 | 7369 | 6.6947
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 10 | 3869 | 9005 | 3869 | 9005 | 7.2993
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 11 | 4612 | 10850 | 4612 | 10850 | 8.2124
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 12 | 5527 | 12218 | 5527 | 12218 | 9.1188
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 13 | 6575 | 13921 | 6575 | 13921 | 9.8254
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 14 | 7991 | 15417 | 7991 | 15417 | 10.6708
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 15 | 9193 | XX | 9193 | 15967.6 | 11.7057
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 16 | 10831 | XX | 10831 | 16518.2 | 12.9729
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 17 | 12946 | XX | 12946 | 17068.8 | 14.9215
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 18 | 14295 | XX | 14295 | 17619.4 | 16.3232
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 19 | 16051 | 18170 | 16051 | 18170 | 17.4036
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 20 | 17808 | 20022 | 17808 | 20022 | 18.094
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 21 | 19666 | 21936 | 19666 | 21936 | 19.1266
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 22 | 21178 | 24418 | 21178 | 24418 | 19.9972
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 23 | 22839 | 26186 | 22839 | 26186 | 20.8274
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 24 | 24873 | 27972 | 24873 | 27972 | 21.8073
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 25 | 26310 | 29397 | 26310 | 29397 | 22.6961
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 26 | 27720 | 30899 | 27720 | 30899 | 23.5601
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 27 | 29113 | 31821 | 29113 | 31821 | 24.5924
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 28 | 30298 |  | 30298 |  | 25.4671
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 29 | 30765 |  | 30765 |  | 25.8056
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | 30 | 31821 |  | 31821 |  | 27
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X | Example Data |  |  | Computed Result
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X
Period | [5 empty] | N | 0 | X | X | X | N | 0 | X | X | X

## Longest Path ES(L)
Period | IEAC(t)sp | PD | ES(L)
|  | 0 |  | Example of applying increasing ES(L) condition for selection of longest path forecasts.
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L) | Performance Path | **** **** **** ES(L) by Period **** **** ****
Period | IEAC(t)sp |  | ES(L) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Period | IEAC(t)sp |  | ES(L) | 1-4-8-10 |  | 1.4815 | 3.2143 | 5.1163 | 5.5556 | 5.4545 | 7.0315 | 8.2051 | 8.1818 | 10
Period | IEAC(t)sp |  | ES(L) | 2-4-8-10 |  |  | 1.0465 | 3.6735 | 5 | 4.7368 | 6.6599 | 8 | 7.9412 | 10
Period | IEAC(t)sp |  | ES(L) | 2-5-9 |  |  |  | 5 | 5.9633 | 6.7925 | 7 | 6.8085 | 7.6596 | 8.7349 | 9.3617 | 10
Period | IEAC(t)sp |  | ES(L) | 3-8-10 |  |  | 2.5 | 4.1584 | 5 | 4.7368 | 6.6599 | 8 | 7.9412 | 10
Period | IEAC(t)sp |  | ES(L) | 7-10 | **** **** **** ES(L) by Period **** **** **** 4: 3.1373; **** **** **** ES(L) by Period **** **** **** 5: 4.0865; **** **** **** ES(L) by Period **** **** **** 6: 4.7059; **** **** **** ES(L) by Period **** **** **** 7: 6.0514; **** **** **** ES(L) by Period **** **** **** 8: 7.4227; **** **** **** ES(L) by Period **** **** **** 9: 7.8947; **** **** **** ES(L) by Period **** **** **** 10: 10
Period | IEAC(t)sp |  | ES(L) | 6-9 | **** **** **** ES(L) by Period **** **** **** 6: 6.5455; **** **** **** ES(L) by Period **** **** **** 7: 7; **** **** **** ES(L) by Period **** **** **** 8: 6.4; **** **** **** ES(L) by Period **** **** **** 9: 7.4118; **** **** **** ES(L) by Period **** **** **** 10: 8.6364; **** **** **** ES(L) by Period **** **** **** 11: 9.3077; **** **** **** ES(L) by Period **** **** **** 12: 10
Period | IEAC(t)sp |  | ES(L) | Total Project |  | 1.4815 | 3.0769 | 4.2857 | 4.9839 | 5.3978 | 6.5175 | 7.0833 | 7.6201 | 8.999 | 9.4516 | 10
Period | IEAC(t)sp |  | ES(L) | These two tables are created using the IEAC(t)sp and ES(L) results from this sheet for each of the project schedule paths. The increasing
Period | IEAC(t)sp |  | ES(L) | condition for ES(L) is then used to identify the appropriate LP forecast. As observed, the value 1.48 in period 2 is greater than 1.05 in period 3.
Period | IEAC(t)sp |  | ES(L) | Thus, the LP forecast for path 2-4-8-10 is identified as an anomaly. The period 3 forecast for path 3-8-10 is then selected. For clarity, the
Period | IEAC(t)sp |  | ES(L) | forecasts chosen as longest path are color-coded lime green, while the anomaly is colored red.
Period | IEAC(t)sp |  | ES(L) | Performance Path | **** **** **** ES(L) by Period **** **** **** 1: **** **** **** Forecast by Period **** **** ****
Period | IEAC(t)sp |  | ES(L) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Period | IEAC(t)sp |  | ES(L) | 1-4-8-10 |  | 13.5 | 9.3333 | 7.8182 | 9 | 11 | 9.9552 | 9.75 | 11 | 10
Period | IEAC(t)sp |  | ES(L) | 2-4-8-10 |  |  | 28.6667 | 10.8889 | 10 | 12.6667 | 10.5106 | 10 | 11.3333 | 10
Period | IEAC(t)sp |  | ES(L) | 2-5-9 |  |  |  | 8 | 8.3846 | 8.8333 | 10 | 11.75 | 11.75 | 11.4483 | 11.75 | 12
Period | IEAC(t)sp |  | ES(L) | 3-8-10 |  |  | 12 | 9.619 | 10 | 12.6667 | 10.5106 | 10 | 11.3333 | 10
Period | IEAC(t)sp |  | ES(L) | 7-10 | **** **** **** Forecast by Period **** **** **** 4: 12.75; **** **** **** Forecast by Period **** **** **** 5: 12.2353; **** **** **** Forecast by Period **** **** **** 6: 12.75; **** **** **** Forecast by Period **** **** **** 7: 11.5676; **** **** **** Forecast by Period **** **** **** 8: 10.7778; **** **** **** Forecast by Period **** **** **** 9: 11.4; **** **** **** Forecast by Period **** **** **** 10: 10
Period | IEAC(t)sp |  | ES(L) | 6-9 | **** **** **** Forecast by Period **** **** **** 6: 9.1667; **** **** **** Forecast by Period **** **** **** 7: 10; **** **** **** Forecast by Period **** **** **** 8: 12.5; **** **** **** Forecast by Period **** **** **** 9: 12.1429; **** **** **** Forecast by Period **** **** **** 10: 11.5789; **** **** **** Forecast by Period **** **** **** 11: 11.8182; **** **** **** Forecast by Period **** **** **** 12: 12
Period | IEAC(t)sp |  | ES(L) | Total Project |  | 13.5 | 9.75 | 9.3333 | 10.0323 | 11.1156 | 10.7403 | 11.2941 | 11.8108 | 11.1124 | 11.6383 | 12
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L) | The ES(L) Increase by Period table shown below provides a method of
Period | IEAC(t)sp |  | ES(L) | automating the selection of the LP forecast and its corresponding ES(L) value.
Period | IEAC(t)sp |  | ES(L) | Performance Path | **** **** **** Forecast by Period **** **** **** 1: **** **** **** ES(L) Increase by Period **** **** ****
Period | IEAC(t)sp |  | ES(L) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Period | IEAC(t)sp |  | ES(L) | 1-4-8-10 | 0 | 1.4815 | 1.7328 | 2.6163 | 2.4183 | 1.368 | 2.3256 | 2.1537 | 1.7818 | 2.5882 | XX | XX
Period | IEAC(t)sp |  | ES(L) | 2-4-8-10 | 0 | XX | XX | 1.1735 | 1.8627 | 0.6503 | 1.954 | 1.9486 | 1.5412 | 2.5882 | XX | XX
Period | IEAC(t)sp |  | ES(L) | 2-5-9 | 0 | XX | XX | 2.5 | 2.826 | 2.7059 | 2.2941 | 0.75711 | 1.2596 | 1.3232 | 0.72534 | 0.69231
Period | IEAC(t)sp |  | ES(L) | 3-8-10 | 0 | XX | 1.0185 | 1.6584 | 1.8627 | 0.6503 | 1.954 | 1.9486 | 1.5412 | 2.5882 | XX | XX
Period | IEAC(t)sp |  | ES(L) | 7-10 | 0 | XX | XX | 0.63725 | 0.94928 | 0.61934 | 1.3455 | 1.3713 | 1.4947 | 2.5882 | XX | XX
Period | IEAC(t)sp |  | ES(L) | 6-9 | 0 | XX | XX | XX | XX | 2.4589 | 2.2941 | 0.3486 | 1.0118 | 1.2246 | 0.67133 | 0.69231
Period | IEAC(t)sp |  | ES(L) | Analysis | **** **** **** ES(L) Increase by Period **** **** **** 1: **** **** **** LPC & ESLP Selection by Period **** **** ****
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L) | Min Value | 0 | 1.4815 | 1.0185 | 0.63725 | 0.94928 | 0.61934 | 1.3455 | 0.3486 | 1.0118 | 1.2246 | 0.67133 | 0.69231
Period | IEAC(t)sp |  | ES(L) | Min Row | 1 | 1 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 3
Period | IEAC(t)sp |  | ES(L) | LPC | #N/A | 13.5 | 12 | 12.75 | 12.2353 | 12.75 | 11.5676 | 12.5 | 12.1429 | 11.5789 | 11.8182 | 12
Period | IEAC(t)sp |  | ES(L) | ESLP | #N/A | 1.4815 | 2.5 | 3.1373 | 4.0865 | 4.7059 | 6.0514 | 6.4 | 7.4118 | 8.6364 | 9.3077 | 10
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)
Period | IEAC(t)sp |  | ES(L)

## #1 Early Finish - 3 wk stop
i EVcum | i PVcum
0 | 0
93 | 93
644 | 644
1710 | 975
2397 | 1275
3060 | 1739
3923 | 2292
4722 | 3331
5743 | 3869
7369 | 4612
9005 | 5527
XX | 6575
XX | 7991
XX | 9193
10850 | 10831
12218 | 12946
13921 | 14295
15417 | 16051
18170 | 17808
20022 | 19666
21936 | 21178
24418 | 22839
26186 | 24873
27972 | 26310
29397 | 27720
30899 | 29113
31821 | 30298
30765
31821

## #2 Late Finish - 4 wk plan stop
i EVcum | i PVcum
0 | 0
93 | 93
644 | 644
975 | 1710
1275 | 2397
1739 | 3060
2292 | 3923
3331 | 4722
3869 | 5743
4612 | 7369
5527 | 9005
6575 | 10850
7991 | 12218
9193 | 13921
10831 | 15417
XX | XX
XX | XX
XX | XX
XX | XX
12946 | 18170
14295 | 20022
16051 | 21936
17808 | 24418
19666 | 26186
21178 | 27972
22839 | 29397
24873 | 30899
26310 | 31821
27720
29113
30298
30765
31821

## #3 Late Finish - work thru stop
i EVcum | i PVcum
0 | 0
93 | 93
644 | 644
975 | 1710
1275 | 2397
1739 | 3060
2292 | 3923
3331 | 4722
3869 | 5743
4612 | 7369
5527 | 9005
6575 | 10850
7991 | 12218
9193 | 13921
10831 | 15417
12946 | XX
14295 | XX
16051 | XX
17808 | XX
19666 | 18170
21178 | 20022
22839 | 21936
24873 | 24418
26310 | 26186
27720 | 27972
29113 | 29397
30298 | 30899
30765 | 31821
31821

## #4 Late Finish - mix stop-plan
i EVcum | i PVcum
0 | 0
93 | 93
644 | 644
975 | 1710
1275 | 2397
1739 | 3060
XX | 3923
XX | 4722
2292 | 5743
3331 | 7369
3869 | 9005
4612 | 10850
5527 | 12218
6575 | 13921
7991 | 15417
9193 | XX
10831 | XX
12946 | XX
14295 | XX
16051 | 18170
17808 | 20022
19666 | 21936
21178 | 24418
22839 | 26186
24873 | 27972
26310 | 29397
27720 | 30899
29113 | 31821
30298
30765
31821

## Case #5 Late Finish - linear
i EVcum | i PVcum
0 | 0
XX | 1
1 | 2
2 | 3
3 | 4
4 | 5
5 | 6
6 | 7
7 | 8
8 | 9
9 | 10
10