## Instructions
ES-LP Calculator Instruction
The ES-LP calculator performs very much like the simple ES calculator. The instruction in blue below is taken from the ES calculator and
remains applicable. The meaning of planned duration is changed. It describes the period of execution and does not account for void periods.
Another difference is PV and EV values are entered to the calculator beginning with the first numerical entry, disregarding when it occurred.
Enter EVcum and PVcum into columns A and B of the EScalc sheet. Note that row 3 is the 1st data entry. Before each use clear all data
in columns A and B below row 2. To insure correctly calculated values, load the entire baseline (periodic values of PVcum) into column B.
Enter PV = BAC one time only. Entering PV = BAC for time periods past the planned duration (PD) will cause the message, ERROR, to
appear instead of computed values for ES, SPI(t), and SV(t). Computed values for SPI(t)mo, SPI(t)cum, SV(t)mo, and SV(t)cum are displayed
in columns I, J, L, and M, respectively.
The cumulative actual time (AT) is in reference to actual performance and shown in column K. The PD for the path is calculated for the PV
entries and is displayed in cell N2. The PD for the project is entered in cell R2. Enter the offset for the start of path performance in cell O2;
offset is the time difference between the project and path execution starts. The AT for the path is shown in column ATLP. The path forecast is
displayed beneath the heading IEAC(t)LP. The ES value representing the path forecast is depicted in the column ES(L). The forecast and path
ES may be one of several for determining which performance path has the longest forecast duration. Clear offset entry before entering data and
performing calculations for another path.
The ES-LP calc sheet produces forecasts and ES(L) values for a single path. The output produced for all paths is analyzed collectively to identify
the longest forecast at each status period. To better understand how this is accomplished, review and the notes and examine the tables at the
Example ES(L) tab. The Example Data and Paralle Data tabs are provided for experimentation and familiarization.
Notes:
1. The ES-LP calculator will provide correct output only when, once path performance commences, the PV and EV path data is
not interrupted by either stop work or down-time conditions. If stop work and/or down-time conditions are present use the ES
Special Case calculator.
2. When determining the LP from all of the path forecasts, ES(L) must not be less than its value for the previous status point. The
forecasts and ES(L) values for all paths are to be merged to apply the ES(L) condition for determining selection of LP for the period.
An example of the process is shown on the Example ES(L) Analysis sheet.

## ES-LP calc
EVcum | PVcum | # Pc=>Sc | Numerator | Denominator | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | PVcount | ATLP | IEAC(t)LP | ES(L) | PDproject
0 | 0 | [8 empty] | 0 |  |  | 0 | 0
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-LP | IEAC(t)LP | ES(L)
BAC Count | 0

## Parallel Data
······ Parallel Project ······
| Period | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Task 1 | PV | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100
| EV | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100
Task 2 | PV | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60
| EV | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60
Task 3 | PV | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40
| EV | 1 | 3 | 4 | 5 | 7 | 8 | 9 | 11 | 12 | 13 | 15 | 16 | 17 | 19 | 20 | 21 | 23 | 24 | 25 | 27 | 28 | 29 | 31 | 32 | 33 | 35 | 36 | 37 | 39 | 40
|  |  | 28 | 42 | 56 | 70 | 84 | 98 | 112 | 126 | 140 | 44 | 48 | 52 | 56 | 60 | 64 | 68 | 72 | 76 | 80 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Total | PV | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 110 | 120 | 130 | 140 | 150 | 160 | 170 | 180 | 190 | 200
| EV | 14 | 29 | 43 | 57 | 72 | 86 | 100 | 115 | 129 | 143 | 148 | 152 | 156 | 161 | 165 | 169 | 174 | 178 | 182 | 187 | 188 | 189 | 191 | 192 | 193 | 195 | 196 | 197 | 199 | 200
Become familiar with the Longest Path forecasting process by experimenting with this data and the Parallel ES(L) Analysis along with the Parallel Forecasts sheets.
The data provided in the above table is for a project having 3 tasks. The tasks are performed in parallel, scheduled to begin and end together. Thus, each task is a serial path
to completion. Note that the project planned duration is 20 periods.
Begin with Task 1. Copy the associated PV and EV data to the ES-LP calc sheet to compute IEAC(t)LP values for all task performance periods. Enter the project PD (20) to
cell R2. Next, copy the computed forecast values to the Parallel ES(L) Analysis sheet. Enter the task name (Task 1) and the associated forecast values to the Forecast by
Period table. Note the instruction in the red area above the table.
Repeat the process for Tasks 2 And 3. Compute the forecasts for the Total Project, as well. Once all calculations have been made and entered to the Parallel ES(L)
Analysis sheet, scroll down to view the IEAC(t)LPc and ESLP Selection by Period table. The selected longest path forecasts are provided in the IEAC(t)LPc row.
View the graphs of forecasts for Total Project, Longest Path, and Final Duration are displayed at the Parallel Forecasts tab.. As you can see, Longest Path is a much better forecast.

## Parallel ES(L) Analysis
Performance Path | **** **** **** ES(L) by Period **** **** **** | [11 empty] | PD = | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
0
0
0
0
0
0
Total Project
Input the forecasts for each path into the Forecast by Period table. If the path execution begins after period 1, leave the preceding
periods blank. Upon entry at each period, the ES(L) values are computed and appear in the ES(L) by Period table above. For the
Total Project forecast, fill periods prior to the 1st period of execution and the remainder of the periods of the table after completion
with #N/A, so that the forecast graph does not plot blank cells.
Performance Path | **** **** **** Forecast by Period **** **** ****
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Total Project | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
The ES(L) Increase by Period table shown below provides a method of automating the selection of the LP forecast and its
corresponding ES(L) value. The resultant forecast using Longest Path is computed and shown in the IEAC(t)LPc & ESLP Selection
by Period table below.
Performance Path | **** **** **** ES(L) Increase by Period **** **** ****
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
0
0
0
0
0
0
Analysis | **** **** **** IEAC(t)LPC & ESLP Selection by Period **** **** ****
Min Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Min Row | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC(t)LPC | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ESLP | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Parallel Forecasts
Parallel Schedule - Forecasts
Period | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
IEAC(t) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC(t)LPc | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Final Duration | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Note: Input the Final Duration to the table above.
The axes for the graph may need adjusting
to have the plots displayed properly.

## Example Data
EVcum | PVcum |  | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | ATLP | IEAC(t)LP | ES(L) | PDproject
|  | Compare your results obtained from using |  |  | 0 |  |  | 2 |  |  | 36
|  | this data to their corresponding values in | 1 | 1 | 1 | 0 | 0 | 3 | 29 | 3.7241
93 |  | columns I, J, L, M, O, P, Q. | 1 | 1 | 2 | 0 | 0 | 4 | 29 | 4.9655
644 |  |  | 2.9375 | 1.6458 | 3 | 1.9375 | 1.9375 | 5 | 18.4051 | 9.7799
1710 |  |  | 1.1636 | 1.5253 | 4 | 0.16356 | 2.1011 | 6 | 19.7018 | 10.9634
2397 |  | Note: This path is planned to begin 9 | 0.63811 | 1.3478 | 5 | -0.36189 | 1.7392 | 7 | 22.0321 | 11.4378
3060 |  | periods after its re-scheduled start. The | 1.3335 | 1.3454 | 6 | 0.33351 | 2.0727 | 8 | 22.0677 | 13.0508
3923 |  | execution actually begins 7 periods early, 2 | 1.0475 | 1.3029 | 7 | 0.04754 | 2.1202 | 9 | 22.7232 | 14.2586
4722 |  | periods after the re-scheduled start. Both | 1.0859 | 1.2758 | 8 | 0.085888 | 2.2061 | 10 | 23.1638 | 15.5415
5743 | 93 | planned values and earned values are entered | 1.3546 | 1.2845 | 9 | 0.35463 | 2.5607 | 11 | 23.0194 | 17.2029
7369 | 644 | to the calculator, disregarding the void | 1.2829 | 1.2844 | 10 | 0.28286 | 2.8436 | 12 | 23.0222 | 18.7645
9005 | 975 | periods. The two period difference in the | 1.1654 | 1.2735 | 11 | 0.16539 | 3.009 | 13 | 23.2007 | 20.1718
10850 | 1275 | re-scheduled start and path start is entered | 0.64681 | 1.2213 | 12 | -0.35319 | 2.6558 | 14 | 24.1073 | 20.9065
12218 | 1739 | in cell O2 to recognize the offset. Thus, the | 1.067 | 1.2094 | 13 | 0.066966 | 2.7228 | 15 | 24.3243 | 22.2
13921 | 2292 | forecast values are in reference to the | 0.91619 | 1.1885 | 14 | -0.083805 | 2.639 | 16 | 24.7178 | 23.3031
15417 | 3331 | re-scheduled start. The PD for the project is | 1.5559 | 1.213 | 15 | 0.55588 | 3.1948 | 17 | 24.2591 | 25.2277
18170 | 3869 | assumed to coincide with the number of cells | 1.0406 | 1.2022 | 16 | 0.040617 | 3.2354 | 18 | 24.4585 | 26.4938
20022 | 4612 | in the PV column. | 1.2209 | 1.2033 | 17 | 0.2209 | 3.4564 | 19 | 24.438 | 27.9892
21936 | 5527 |  | 1.32 | 1.2098 | 18 | 0.31995 | 3.7763 | 20 | 24.3178 | 29.6079
24418 | 6575 |  | 1.1374 | 1.206 | 19 | 0.13741 | 3.9137 | 21 | 24.3883 | 30.9984
26186 | 7991 |  | 1.2672 | 1.209 | 20 | 0.2672 | 4.1809 | 22 | 24.3317 | 32.5502
27972 | 9193 |  | 1.0588 | 1.2019 | 21 | 0.058758 | 4.2397 | 23 | 24.4646 | 33.8448
29397 | 10831 |  | 1.155 | 1.1998 | 22 | 0.15495 | 4.3946 | 24 | 24.5046 | 35.2587
30899 | 12946 |  | 0.60538 | 1.1739 | 23 | -0.39462 | 4 | 25 | 25 | 36
31821 | 14295
16051
17808
19666
21178
22839
24873
26310
27720
29113
30298
31821

## Example ES(L) Analysis
Performance Path | **** **** **** ES(L) by Period **** **** ****
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1-4-8-10 |  | 1.4815 | 3.2143 | 5.1163 | 5.5556 | 5.4545 | 7.0315 | 8.2051 | 8.1818 | 10
2-4-8-10 |  |  | 1.0465 | 3.6735 | 5 | 4.7368 | 6.6599 | 8 | 7.9412 | 10
2-5-9 |  |  |  | 5 | 5.9633 | 6.7925 | 7 | 6.8085 | 7.6596 | 8.7349 | 9.3617 | 10
3-8-10 |  |  | 2.5 | 4.1584 | 5 | 4.7368 | 6.6599 | 8 | 7.9412 | 10
7-10 |  |  |  | 3.1373 | 4.0865 | 4.7059 | 6.0514 | 7.4227 | 7.8947 | 10
6-9 | [5 empty] | 6.5455 | 7 | 6.4 | 7.4118 | 8.6364 | 9.3077 | 10
Total Project |  | 1.4815 | 3.0769 | 4.2857 | 4.9839 | 5.3978 | 6.5175 | 7.0833 | 7.6201 | 8.999 | 9.4516 | 10
These two tables are created using the results from this calculator for each of the project schedule paths. The increasing condition for ES(L) is then used to
identify the appropriate LP forecast. As observed, the value 1.48 in period 2 is greater than 1.05 in period 3. Thus, the LP forecast for path 2-4-8-10 is identified
as an anomaly. The period 3 forecast for path 3-8-10 is then selected. For clarity, the forecasts chosen as longest path are color-coded lime green, while the
anomaly is colored red.
Performance Path | **** **** **** Forecast by Period **** **** ****
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1-4-8-10 |  | 13.5 | 9.3333 | 7.8182 | 9 | 11 | 9.9552 | 9.75 | 11 | 10
2-4-8-10 |  |  | 28.6667 | 10.8889 | 10 | 12.6667 | 10.5106 | 10 | 11.3333 | 10
2-5-9 |  |  |  | 8 | 8.3846 | 8.8333 | 10 | 11.75 | 11.75 | 11.4483 | 11.75 | 12
3-8-10 |  |  | 12 | 9.619 | 10 | 12.6667 | 10.5106 | 10 | 11.3333 | 10
7-10 |  |  |  | 12.75 | 12.2353 | 12.75 | 11.5676 | 10.7778 | 11.4 | 10
6-9 | [5 empty] | 9.1667 | 10 | 12.5 | 12.1429 | 11.5789 | 11.8182 | 12
Total Project |  | 13.5 | 9.75 | 9.3333 | 10.0323 | 11.1156 | 10.7403 | 11.2941 | 11.8108 | 11.1124 | 11.6383 | 12
The ES(L) Increase by Period table shown below provides a method of automating the selection of the LP forecast and its corresponding ES(L) value.
Performance Path | **** **** **** ES(L) Increase by Period **** **** ****
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1-4-8-10 |  | 1.4815 | 1.7328 | 2.6163 | 2.4183 | 1.368 | 2.3256 | 2.1537 | 1.7818 | 2.5882
2-4-8-10 |  |  | XX | 1.1735 | 1.8627 | 0.6503 | 1.954 | 1.9486 | 1.5412 | 2.5882
2-5-9 |  |  |  | 2.5 | 2.826 | 2.7059 | 2.2941 | 0.75711 | 1.2596 | 1.3232 | 0.72534 | 0.69231
3-8-10 |  |  | 1.0185 | 1.6584 | 1.8627 | 0.6503 | 1.954 | 1.9486 | 1.5412 | 2.5882
7-10 |  |  |  | 0.63725 | 0.94928 | 0.61934 | 1.3455 | 1.3713 | 1.4947 | 2.5882
6-9 | [5 empty] | 2.4589 | 2.2941 | 0.3486 | 1.0118 | 1.2246 | 0.67133 | 0.69231
Analysis | **** **** **** ES(L) Increase by Period **** **** ****
Min Value | 0 | 1.4815 | 1.0185 | 0.63725 | 0.94928 | 0.61934 | 1.3455 | 0.3486 | 1.0118 | 1.2246 | 0.67133 | 0.69231
Min Row | #N/A | 1 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 3
LPC | #N/A | 13.5 | 12 | 12.75 | 12.2353 | 12.75 | 11.5676 | 12.5 | 12.1429 | 11.5789 | 11.8182 | 12
ESLP | #N/A | 1.4815 | 2.5 | 3.1373 | 4.0865 | 4.7059 | 6.0514 | 6.4 | 7.4118 | 8.6364 | 9.3077 | 10