## Description
P-Factor Description
General Description
The P-Factor is a measure of how closely the execution of the project follows the plan. It is an indicator of schedule
proficiency. The calculation of the P-Factor is complex. It requires records be maintained meticulously throughout the
execution of the project. As an example for understanding, the P-Factor could be approximated, for example, from time-
phased milestones. The milestones which should have been completed are identified by the value of Earned Schedule (ES).
The milestones that have actually been completed are matched to the planned ones identified. Crudely, the P-Factor
could be calculated from the two numbers: 1) the number of planned milestones identified by ES, and 2) the number of
actual milestones accomplished which match the identified planned milestones. The approximation of the P-Factor would
be the quotient of the number of matching actuals to the number of planned milestones. The calculation performed in this
set of spreadsheets is much more refined and accurate than the milestone approximation example described. The
maximum value the P-Factor can have is 1.0, when the execution of the plan is adhered to, perfectly.
Example Data & Calculations
The Example Data sheet has been included to help illustrate the descriptions. The availability of the data allows the user
to gain familiarity with the operation of the calculator and its required data entry. Entering the data and comparing values
obtained against the existing results is instructive. The example data is useful for future reference and to refresh one's
memory.To apply to a new project, simply clear the example data from the Task PV @ PT and Task EV @ AT sheets and
enter the project data for analysis. All cells for these two sheets not having numeric entry are to be filled with "x".
Worksheet Descriptions
Each worksheet has a brief instruction for its use appearing near the top of the sheet. After some usage familiarity it
may be enough of a reminder. However, for infrequent use the descriptions below will be of benefit. The worksheets can
handle a project of 60 months duration with as many as 196 tasks.
There are three worksheets fundamental to the P-Factor calculator: Task PV @ PT, Task EV @ AT, and P-Calc.
The Task PV @ PT sheet is a record of the Performance Measurement Baseline (PMB), task by task. The task
identifications are entered to the Task PV @ AT sheet and are linked to the other worksheets. The planned values for each
task are entered cumulatively for each periodic time increment, beginning at their planned time. Once the full planned value
is accrued, it is entered into the subsequent planned periods through the planned completion. The Task PV @ PT sheet,
as with the other two sheets, has the capacity of 196 tasks.
The Task EV @ AT sheet is the record of project performance, task by task. The cumulative earned value for each task is
entered for each time period, thereby accruing to full PV, as it occurs. Once the full value has been achieved it is
recorded in the subsequent periods until project completion. The Task PV and Task EV data sheets are critical to the
calculation of the P-Factor. To perform the P-Factor calculation at a specific period requires the time-related EV accrued
for each task as well as cumulative values for PV(n) and PV(n+1) for each task, where n is defined to be the number of
complete time increments of the PMB as determined from the calculation of ES. Also required for the calculations are the
planned and actual Start and Completion Dates for the tasks. The actual dates entered to the Task EV @ AT sheet are not
required to be exact, but must coincide with the first and last periods in which EV is accrued.
The Data & P-Factor sheet requires a small amount of data entry. Instruction is provided on the sheet as to the data
required and where to enter it. The Percent Rework entry is either "x" or a decimal value representing a constant
percentage of rework throughout the project. When "x" is entered the percentage of rework is calculated by an algorithm
which generates rework percentage values decreasing with increasing percent complete. Selecting "x" is recommended
for most applications. Once the initial data entry is made to the Task PV @ PT and Data & P-Factor sheets and the
actual task performance is being recorded in the Task EV @ AT sheet, the P-Factor will be calculated and the value will
appear on the Data & Results sheet. The calculated value for the P-Factor and the Actual Cost (AC) are recorded on the
Data and P-Factor sheet according to the instruction provided. The recorded values facilitate other possible analysis.
The P-Calc sheet calculates the value of the P-Factor from the data input to the Task PV @ PT, Task EV @ AT, and the
Data & P-Factor sheets. The calculated value is returned to the Data & P-Factor sheet for recording and further
calculations. All of the data areas of the sheet are user accessible and thus can be readily used for creating graphs or
other analysis and presentation forms.
The Mgmt Review sheet provides information as to which tasks warrant management attention. Under the Flag column
indication is given as to the possibility of "Future Rework" or the existence of a "Constraint or Impediment." The amount of
the EV problem is shown in the next column, EV Difference. The remaining EV to be worked on the task is provided in the
next column. It is to be noted that when a task is flagged as having the possibility of a constraint or impediment, the
associated EV Difference has a negative sign. The negative sign is another indication that the project execution of the task
is lagging the ES planned performance.Managers should focus their attention on alleviating the contraints or impediments
for the tasks identified with those possible conditions.
The ES Calc sheet is included to perform the necessary earned schedule calculations. No entry to these sheets is required.

## Step by Step
Step by Step Instruction
1. Enter the Task Identification names into the Task PV @ PT sheet. Then complete the other data needed:
planned dates for task start and completion and the task planned values. Note that the planned
values are cumulative with each successive period. Once the full PV is shown it is recorded in the
successive periods through the planned completion. After completing the PMB entry note the Data Status
above the Start and Completion Date columns. When "Data OK" is displayed, the data entry is complete.
When "Entry Fault" appears, scroll right to the Data Entry Checks area. The tasks having entry faults are
identified.
2. Enter to the Data & P-Factor sheet the project reference date; it will be the the 1st day of the 1st full month
of reporting, when the performance data for the preceding partial month is included. Otherwise enter the
project start date for the reference date. Enter the negotiated completion date, and Budget at Completion
(BAC). Entry of the amount of the Total Allocated Budget (TAB) is optional. When the percent rework
algorithm is to be used, enter a non-numeric ("x") to the Data & P-Factor sheet. Otherwise, enter the value
assumed for percent rework. The reported cumulative value for EV and its corresponding AT value are
entered once the task values of EV have been entered to the Task EV @ AT sheet. The reported earned
value (EV) is cross-checked against the total of the individual task values entered to the Task EV @ AT
sheet. Enter the time period (M, W, D) used for reporting and analysis into Time Period Selector.
3. Update the Task EV @ AT with the latest performance data. Just as for the Task PV @ PT sheet, when the
full EV is accrued, the value is carried in successive periods until project completion. After each periodic
data entry note the Data Status above the Start and Completion Date columns. When "Data OK" is
displayed, the data entry is complete. When "Entry Fault" appears scroll right to the Data Entry Checks
area. The tasks having entry faults are identified. Enter the date performance accounting begins in cell B3.
4. The P-Factor computed value will appear on the Data & P-Factor sheet once all of the requisite data is
entered. It is possible to have an error display either in the P-Factor cell or in the EV recorded -
EV reported cell. Generally, the error is made in the data entry to the Task EV @ AT sheet. The
P - Calc sheet may be of help in identifying and locating the error.
5. On the Data & P-Factor sheet record the value of the P-Factor and the actual cost in the AC & P-Factor
Table. These results are available for additional analysis. The tasks identified as having potential future
rework and present constraints or impediments are shown on the Mgmt Review sheet.
Note: If application is for Longest Path (LP), the path execution may start several periods after the beginning of
the project. For examination of paths, enter the date for the start of project to cell B3 on the PV @ PT sheet.
Enter to cell B3 on EV @ AT sheet the date of actual start of path performance.

## Task PV @ PT
Instruction: Enter PVcum for the specific tasks at the appropriate Planned Time. The sum for each successive time increment describes the PMB. Below the Planned Time numbers enter the end date of the status period (e.g., end of the month date). | [66 empty] | Data Entry Checks
| Data Status | DATA OK |  | Planned Time | [60 empty] | PV |  | ******* Start ******* |  |  | ***** Complete ***** |  |  | Planned Start | Planned Completion
Task ID | Start Dt (plan) | Compl Dt (plan) | Total Task PV | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | ES | Selected |  |  | 1st EV | St Dt | Last EV | Comp Dt |  | 2004-12-16 | 2005-10-31
| 2004-12-16 |  | 185 | 2005-01-31 | 2005-02-28 | 2005-03-31 | 2005-04-30 | 2005-05-31 | 2005-06-30 | 2005-07-31 | 2005-08-31 | 2005-09-30 | 2005-10-31 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | [35 empty] | 6.9 | 6 | 7 | Task PV | Period | Period | Period | Period | PVe <> PV? | 10 | 10 | Nr of Dates in Plan
#1 | 2004-12-16 | 2005-03-31 | 15 | 5 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0 | 15 | 15 | 15 | 1 | OK | 3 | OK | OK
#2 | 2005-03-01 | 2005-03-31 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 1 | 10 | 10 | 10 | 3 | OK | 3 | OK | OK
#3 | 2005-03-01 | 2005-05-31 | 30 | 0 | 0 | 10 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 2 | 30 | 30 | 30 | 3 | OK | 5 | OK | OK
#4 | 2005-04-01 | 2005-05-31 | 10 | 0 | 0 | 0 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 3 | 10 | 10 | 10 | 4 | OK | 5 | OK | OK
#5 | 2005-04-01 | 2005-06-30 | 15 | 0 | 0 | 0 | 5 | 10 | 15 | 15 | 15 | 15 | 15 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 4 | 15 | 15 | 15 | 4 | OK | 6 | OK | OK
#6 | 2005-05-01 | 2005-06-30 | 10 | 0 | 0 | 0 | 0 | 5 | 10 | 10 | 10 | 10 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 5 | 10 | 10 | 10 | 5 | OK | 6 | OK | OK
#7 | 2005-03-01 | 2005-07-31 | 50 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 50 | 50 | 50 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 6 | 40 | 50 | 50 | 3 | OK | 7 | OK | OK
#8 | 2005-05-01 | 2005-08-31 | 20 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 20 | 20 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 7 | 10 | 15 | 20 | 5 | OK | 8 | OK | OK
#9 | 2005-07-01 | 2005-09-30 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 15 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 8 | 0 | 5 | 15 | 7 | OK | 9 | OK | OK
#10 | 2005-09-01 | 2005-10-31 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 9 | 0 | 0 | 10 | 9 | OK | 10 | OK | OK
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 10 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 11 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 12 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 13 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 14 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 15 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 16 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 17 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 18 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 19 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 20 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 21 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 22 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 23 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 24 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 25 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 26 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 27 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 28 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 29 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 30 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 31 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 32 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 33 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 34 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 35 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 36 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 37 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 38 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 39 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 40 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 41 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 42 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 43 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 44 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 45 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 46 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 47 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 48 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 49 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 50 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 51 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 52 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 53 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 54 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 55 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 56 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 57 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 58 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 59 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 60 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 61 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 62 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 63 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 64 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 65 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 66 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 67 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 68 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 69 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 70 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 71 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 72 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 73 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 74 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 75 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 76 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 77 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 78 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 79 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 80 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 81 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 82 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 83 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 84 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 85 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 86 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 87 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 88 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 89 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 90 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 91 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 92 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 93 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 94 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 95 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 96 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 97 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 98 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 99 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 100 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 101 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 102 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 103 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 104 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 105 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 106 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 107 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 108 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 109 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 110 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 111 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 112 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 113 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 114 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 115 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 116 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 117 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 118 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 119 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 120 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 121 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 122 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 123 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 124 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 125 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 126 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 127 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 128 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 129 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 130 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 131 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 132 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 133 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 134 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 135 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 136 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 137 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 138 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 139 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 140 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 141 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 142 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 143 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 144 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 145 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 146 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 147 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 148 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 149 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 150 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 151 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 152 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 153 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 154 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 155 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 156 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 157 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 158 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 159 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 160 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 161 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 162 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 163 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 164 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 165 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 166 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 167 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 168 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 169 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 170 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 171 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 172 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 173 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 174 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 175 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 176 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 177 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 178 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 179 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 180 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 181 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 182 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 183 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 184 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 185 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 186 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 187 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 188 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 189 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 190 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 191 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 192 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 193 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 194 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 195 | x | x | x | x | x | x | x | x
Task Identifier | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 196 | x | x | x | x | x | x | x | x
| Performance Measurement Baseline |  |  | 5 | 10 | 45 | 75 | 115 | 140 | 160 | 170 | 180 | 185 | [53 empty] | Fault Count |  | 0 |  | 0

## Task EV @ AT
Instruction: Enter EVcum for the specific tasks at the appropriate Actual Time. Below the Actual Time period numbers enter the end date of the status period (e.g., end of the month date). | [64 empty] | Data Entry Checks
| Data Status | DATA OK | Actual Time | [60 empty] | AT | ******* Start ******* |  |  | ***** Complete *****
Task ID | Start Dt (actual ) | Compl Dt (actual) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 |  | 9 |  | 1st EV | St Dt | Last EV | Comp Dt
| 2005-01-16 |  | 2005-01-31 | 2005-02-28 | 2005-03-31 | 2005-04-30 | 2005-05-31 | 2005-06-30 | 2005-07-31 | 2005-08-31 | 2005-09-30 | 2005-10-31 | 2005-11-30 | 2005-12-31 | [49 empty] | Selected | Task PV | Period | Period | Period | Period | EV <> PV?
#1 | 2005-02-01 | 2005-04-30 | 0 | 5 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 0 | 15 | 15 | 2 | OK | 4 | OK | OK
#2 | 2005-04-01 | 2005-05-31 | 0 | 0 | 0 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 1 | 10 | 10 | 4 | OK | 5 | OK | OK
#3 | 2005-03-01 | 2005-05-31 | 0 | 0 | 10 | 22 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 2 | 30 | 30 | 3 | OK | 5 | OK | OK
#4 | 2005-03-01 | 2005-05-31 | 0 | 0 | 5 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 3 | 10 | 10 | 3 | OK | 5 | OK | OK
#5 | 2005-04-01 | 2005-07-31 | 0 | 0 | 0 | 5 | 8 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 4 | 15 | 15 | 4 | OK | 7 | OK | OK
#6 | 2005-06-01 | 2005-07-31 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 5 | 10 | 10 | 6 | OK | 7 | OK | OK
#7 | 2005-04-01 | 2005-09-30 | 0 | 0 | 0 | 10 | 20 | 30 | 39 | 46 | 50 | 50 | 50 | 50 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 6 | 50 | 50 | 4 | OK | 9 | OK | OK
#8 | 2005-07-01 | 2005-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 13 | 18 | 20 | 20 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 7 | 13 | 20 | 7 | OK | 11 | OK | OK
#9 | 2005-09-01 | 2005-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 15 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 8 | 5 | 15 | 9 | OK | 11 | OK | OK
#10 | 2005-10-01 | 2005-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 9 | 0 | 10 | 10 | OK | 12 | OK | OK
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 10 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 11 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 12 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 13 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 14 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 15 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 16 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 17 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 18 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 19 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 20 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 21 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 22 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 23 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 24 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 25 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 26 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 27 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 28 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 29 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 30 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 31 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 32 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 33 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 34 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 35 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 36 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 37 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 38 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 39 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 40 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 41 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 42 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 43 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 44 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 45 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 46 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 47 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 48 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 49 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 50 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 51 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 52 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 53 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 54 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 55 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 56 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 57 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 58 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 59 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 60 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 61 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 62 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 63 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 64 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 65 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 66 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 67 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 68 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 69 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 70 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 71 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 72 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 73 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 74 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 75 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 76 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 77 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 78 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 79 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 80 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 81 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 82 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 83 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 84 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 85 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 86 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 87 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 88 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 89 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 90 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 91 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 92 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 93 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 94 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 95 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 96 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 97 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 98 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 99 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 100 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 101 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 102 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 103 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 104 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 105 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 106 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 107 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 108 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 109 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 110 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 111 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 112 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 113 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 114 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 115 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 116 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 117 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 118 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 119 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 120 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 121 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 122 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 123 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 124 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 125 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 126 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 127 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 128 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 129 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 130 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 131 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 132 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 133 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 134 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 135 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 136 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 137 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 138 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 139 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 140 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 141 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 142 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 143 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 144 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 145 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 146 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 147 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 148 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 149 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 150 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 151 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 152 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 153 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 154 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 155 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 156 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 157 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 158 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 159 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 160 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 161 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 162 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 163 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 164 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 165 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 166 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 167 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 168 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 169 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 170 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 171 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 172 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 173 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 174 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 175 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 176 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 177 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 178 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 179 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 180 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 181 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 182 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 183 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 184 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 185 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 186 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 187 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 188 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 189 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 190 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 191 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 192 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 193 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 194 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
Task Identifier | x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 195 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
| x | x | [12 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 196 | x | x | x | x | x | x | x | bar: 2005-01-31 to 2005-12-31
| EV Accrued |  | x | 5 | 25 | 66 | 93 | 113 | 133 | 144 | 158 | 172 | 183 | 185 | [50 empty] | Fault Count |  | 0 |  | 0
| Total PV | 185 | 5 | 10 | 45 | 75 | 115 | 140 | 160 | 170 | 180 | 185

## Example Data
Planned Time
Task ID | Start Dt (plan) | Compl Dt (plan) | Total Task PV | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| 2004-12-16 |  | 185 | 2005-01-31 | 2005-02-28 | 2005-03-31 | 2005-04-30 | 2005-05-31 | 2005-06-30 | 2005-07-31 | 2005-08-31 | 2005-09-30 | 2005-10-31
#1 | 2004-12-16 | 2005-03-31 | 15 | 5 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
#2 | 2005-03-01 | 2005-03-31 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
#3 | 2005-03-01 | 2005-05-31 | 30 | 0 | 0 | 10 | 20 | 30 | 30 | 30 | 30 | 30 | 30
#4 | 2005-04-01 | 2005-05-31 | 10 | 0 | 0 | 0 | 5 | 10 | 10 | 10 | 10 | 10 | 10
#5 | 2005-04-01 | 2005-06-30 | 15 | 0 | 0 | 0 | 5 | 10 | 15 | 15 | 15 | 15 | 15
#6 | 2005-05-01 | 2005-06-30 | 10 | 0 | 0 | 0 | 0 | 5 | 10 | 10 | 10 | 10 | 10
#7 | 2005-03-01 | 2005-07-31 | 50 | 0 | 0 | 10 | 20 | 30 | 40 | 50 | 50 | 50 | 50
#8 | 2005-05-01 | 2005-08-31 | 20 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 20 | 20
#9 | 2005-07-01 | 2005-09-30 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 15
#10 | 2005-09-01 | 2005-10-31 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10
Actual Time
Task ID | Start Dt (actual ) | Compl Dt (actual) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| 2005-01-16 |  | 2005-01-31 | 2005-02-28 | 2005-03-31 | 2005-04-30 | 2005-05-31 | 2005-06-30 | 2005-07-31 | 2005-08-31 | 2005-09-30 | 2005-10-31 | 2005-11-30 | 2005-12-31
#1 | 2005-02-01 | 2005-04-30 | 0 | 5 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
#2 | 2005-04-01 | 2005-05-31 | 0 | 0 | 0 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
#3 | 2005-03-01 | 2005-05-31 | 0 | 0 | 10 | 22 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
#4 | 2005-03-01 | 2005-05-31 | 0 | 0 | 5 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
#5 | 2005-04-01 | 2005-07-31 | 0 | 0 | 0 | 5 | 8 | 13 | 15 | 15 | 15 | 15 | 15 | 15
#6 | 2005-06-01 | 2005-07-31 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 10 | 10 | 10 | 10 | 10
#7 | 2005-04-01 | 2005-09-30 | 0 | 0 | 0 | 10 | 20 | 30 | 39 | 46 | 50 | 50 | 50 | 50
#8 | 2005-07-01 | 2005-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 13 | 18 | 20 | 20
#9 | 2005-09-01 | 2005-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 15
#10 | 2005-10-01 | 2005-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 10
|  | P-Factor | No Data | 1 | 0.57143 | 0.84848 | 0.90323 | 0.95796 | 0.96541 | 0.97222 | 0.99051 | 0.98256 | 1 | 1

## Data & P-Factor
Data & P-Factor Result |  |  |  |  | AC & P-Factor Table
EV reported = EV recorded | Yes EVrep-EVcalc | Check of accuracy of data entry to the Task EV @ AT sheet. If "No," review data entry. |  |  | AT & P-Factor Displayed
P-Factor | 0.99051 | Consult P-Calc sheet when error appears. Generally, a data entry error to the Task EV @ AT sheet is the |  |  | AT = | 9 | P-Factor = | 0.99051
problem.
[5 empty] | AT | AC | P-Factor
Planned Start Date | 2004-12-16 | Date obtained from Task PV @ PT sheet. |  |  | 1 | 0 | No Data
Planned Completion Date | 2005-10-31 | Date obtained from Task PV @ PT sheet |  |  | 2 | 5 | 1
Negotiated Completion Date | 2005-11-30 | Enter negotiated completion date. |  |  | 3 | 25 | 0.57143
Project Reference Date | 2005-01-01 | Enter start date of 1st full month of performance, when the first observation includes a partial month plus the |  |  | 4 | 77 | 0.84848
|  | first full month. Otherwise, enter planned start date. For weekly performance enter planned start date. |  |  | 5 | 112 | 0.90323
[5 empty] | 6 | 132 | 0.95796
Planned Duration | 10.5 | Computed from Start & Completion entries |  |  | 7 | 159 | 0.96541
Planned Periods | 10 | Computed from Reference and Completion entries |  |  | 8 | 174 | 0.97222
Negotiated Duration | 11.4667 | Computed project duration from negotiated completion date and planned start date |  |  | 9 | 194 | 0.99051
[5 empty] | 10 | 214 | 0.98256
Earned Schedule @ AT | 6.9 | Computed ES value corresponding to AT. ES is computed using the V1 calculator. |  |  | 11 | 229 | 1
Actual Time | 9 | Enter the number of the status period |  |  | 12 | 231 | 1
Earned Value cum Reported | 158 | Retrieves cumulative value for EV reported in status report |  |  | 13
14
Budget at Completion | 185 | Enter Budget at Completion |  |  | 15
Total Allocated Budget | 185 | Enter the Total Allocated Budget (TAB = BAC + Management Reserve) (Entry is optional) |  |  | 16
17
Percent Rework | x | When the percent rework algorithm is to be used, enter a non-numeric ("x"). Otherwise, enter decimal value |  |  | 18
|  | representing rework percentage for tasks performed early with respect to the plan (e.g., 0.50 - meaning 50%) |  |  | 19
20
Actual Cost & P-Factor Recording |  |  |  |  | 21
22
Scroll right on this sheet to find the AC & P-Factor Table. As actual cost and P-Factor values are known record them in the table corresponding to the |  |  |  |  | 23
appropriate reporting period (AT). The AC value is simply entered. The P-Factor is copied and then pasted (special - values) to the cell beneath the P-Factor |  |  |  |  | 24
heading corresponding to the number in the AT column equal to the AT value displayed. The numbers entered facilitate other possible analysis. |  |  |  |  | 25
26
27
28
| Time Period Selector |  |  |  | 29
| Period |  | M | Enter letter designator | 30
| Month |  | M |  | 31
| Week |  | W |  | 32
| Day |  | D |  | 33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## Mgmt Review
Tasks for Management Review
Flag | EV Difference | EV Remaining | Task ID | Task PV | Task EV | EVc - PVi | PVc - EVi | EVi > PVi | PVi > EVi
---------------- | --------------- | 0 | #1 | 15 | 15 | 0 | 0 | 0 | 0
---------------- | --------------- | 0 | #2 | 10 | 10 | 0 | 0 | 0 | 0
---------------- | --------------- | 0 | #3 | 30 | 30 | 0 | 0 | 0 | 0
---------------- | --------------- | 0 | #4 | 10 | 10 | 0 | 0 | 0 | 0
---------------- | --------------- | 0 | #5 | 15 | 15 | 0 | 0 | 0 | 0
---------------- | --------------- | 0 | #6 | 10 | 10 | 0 | 0 | 0 | 0
Future Rework | 1 | 0 | #7 | 50 | 50 | 1 | 0 | 0 | 0
Constraint or Impediment | -1.5 | 7 | #8 | 20 | 13 | 0 | 0 | 0 | 1.5
Future Rework | 0.5 | 10 | #9 | 15 | 5 | 0 | 0 | 0.5 | 0
---------------- | --------------- | 10 | #10 | 10 | 0 | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0
---------------- | --------------- | x | Task Identifier | x | x | 0 | 0 | 0 | 0

## P - Calc (hidden)
Data & Calculation of P-Factor
Task ID | Start Dt (plan) | Compl Dt (plan) | Task PV | Start Dt (actual ) | Compl Dt (actual) | Task EV | Start Dur (plan) | Compl Dur (plan) | Start Dur (actual ) | Compl Dur (actual) | C or S (plan) | C or S (actual) | PVi(n+1) | PVi(n) | PVi | EVc - PVi | PVc - EVi | EVi > PVi | PVi > EVi | Ac & Pc | EVi = PVi | ES Value | Sum ( PVc - EVi ) | Sum (EVc - PVi)
#1 | 2004-12-16 | 2005-03-31 | 15 | 2005-02-01 | 2005-04-30 | 15 | -0.5 | 3 | 1 | 3.9667 | C | C | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 6.9 | 0 | 1
#2 | 2005-03-01 | 2005-03-31 | 10 | 2005-04-01 | 2005-05-31 | 10 | 2 | 3 | 3 | 5 | C | C | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | AT Value | Sum (PVi > EVi) | Sum (EVi > PVi)
#3 | 2005-03-01 | 2005-05-31 | 30 | 2005-03-01 | 2005-05-31 | 30 | 2 | 5 | 2 | 5 | C | C | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 9 | 1.5 | 0.5
#4 | 2005-04-01 | 2005-05-31 | 10 | 2005-03-01 | 2005-05-31 | 10 | 3 | 5 | 2 | 5 | C | C | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Proj Ref Dt = | 2005-01-01 | Check Sums =
#5 | 2005-04-01 | 2005-06-30 | 15 | 2005-04-01 | 2005-07-31 | 15 | 3 | 5.9667 | 3 | 7 | C | C | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | Plan St Date = | 2004-12-16 | 3.5527e-15
#6 | 2005-05-01 | 2005-06-30 | 10 | 2005-06-01 | 2005-07-31 | 10 | 4 | 5.9667 | 5 | 7 | C | C | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Plan Comp Dt = | 2005-10-31 | Time Units
#7 | 2005-03-01 | 2005-07-31 | 50 | 2005-04-01 | 2005-09-30 | 50 | 2 | 7 | 3 | 8.9667 | S | C | 50 | 40 | 49 | 1 | 0 | 0 | 0 | 0 | 0 | Plan Duration = | 10.5 | M
#8 | 2005-05-01 | 2005-08-31 | 20 | 2005-07-01 | 2005-11-30 | 13 | 4 | 8 | 6 | 10.9667 | S | S | 15 | 10 | 14.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1st Mo Fraction = | 0.5 | 30
#9 | 2005-07-01 | 2005-09-30 | 15 | 2005-09-01 | 2005-11-30 | 5 | 6 | 8.9667 | 8 | 10.9667 | S | S | 5 | 0 | 4.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | PVcum = | 158 | Compare EV
#10 | 2005-09-01 | 2005-10-31 | 10 | 2005-10-01 | 2005-12-31 | 0 | 8 | 10 | 9 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EVcum (sum EV) = | 158 | Yes PV-EVcalc
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EVcum (reported) = | 158 | Yes EVrep-EVcalc
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EV(p) = | 156.5
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | P - Factor = | 0.99051 | 0.99051
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | P-Factor computed
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Adj Fac (50%) = | 0.99684 | though conditions
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | aren't satisfied.
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan Complete = | 90
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan Incomplete = | 68
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan Total (C + I) = | 158
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EV(p) Breakdown
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sum Complete = | 90
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sum EVc > PVi = | 49
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sum PVc > EVi = | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sum EVi > PVi = | 4.5
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sum PVi > EVi = | 13
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sum EVi = PVi = | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total = | 156.5
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total EV - EV(p) = | 1.5
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Identifier | x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0
| x | x | x | x | x | x | x | x | x | x | 0 | 0 | x | x | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ES Calc (hidden)
EVcum | PVcum | # Pc=>Sc | Numerator | Denominator | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | PMB | 5 | 10 | 45 | 75 | 115 | 140 | 160 | 170 | 180 | 185
0 | 0 | [8 empty] | 1 |  |  | EV | x | 5 | 25 | 66 | 93 | 113 | 133 | 144 | 158 | 172 | 183 | 185
5 | 5 | 1 | 0 | 5 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | -1 | 0
25 | 10 | 2 | 15 | 35 | 0.42857 | 2.4286 | 1.4286 | 1.4286 | 1.2143 | 3 | 0.42857 | -0.57143 | 1
66 | 45 | 3 | 21 | 30 | 0.7 | 3.7 | 1.2714 | 1.2714 | 1.2333 | 4 | 0.27143 | -0.3 | 2
93 | 75 | 4 | 18 | 40 | 0.45 | 4.45 | 0.75 | 0.75 | 1.1125 | 5 | -0.25 | -0.55 | 3 |  | AT | ES @ AT |  | PMB "x" | EV "x" |  | Max PMB | PMB # | EV #
113 | 115 | 4 | 38 | 40 | 0.95 | 4.95 | 0.5 | 0.5 | 0.99 | 6 | -0.5 | -1.05 | 4 |  | 9 | 6.9 |  | 0 | 1 |  | 185 | 9 | 11
133 | 140 | 5 | 18 | 25 | 0.72 | 5.72 | 0.77 | 0.77 | 0.95333 | 7 | -0.23 | -1.28 | 5
144 | 160 | 6 | 4 | 20 | 0.2 | 6.2 | 0.48 | 0.48 | 0.88571 | 8 | -0.52 | -1.8 | 6
158 | 170 | 6 | 18 | 20 | 0.9 | 6.9 | 0.7 | 0.7 | 0.8625 | 9 | -0.3 | -2.1 | 7
172 | 180 | 8 | 2 | 10 | 0.2 | 8.2 | 1.3 | 1.3 | 0.91111 | 10 | 0.3 | -1.8 | 8
183 | 185 | 9 | 3 | 5 | 0.6 | 9.6 | 1.4 | 1.4 | 0.96 | 11 | 0.4 | -1.4 | 9
185 |  | 10 | 0 | -185 | 0 | 10 | 0.4 | 0.4 | 0.90909 | 12 | -0.6 | -2 | 10
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 11
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 12
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 13
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 14
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 15
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 16
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 17
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 18
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 19
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 20
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 21
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 22
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 23
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 24
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 25
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 26
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 27
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 28
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 29
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 30
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 31
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 32
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 33
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 34
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 35
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 36
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 37
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 38
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 39
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 40
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 41
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 42
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 43
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 44
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 45
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 46
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 47
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 48
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 49
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 50
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 51
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 52
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 53
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 54
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 55
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 56
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 57
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 58
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 59
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 60
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 61
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 62
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 63
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 64
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 65
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 66
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 67
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 68
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 69
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 70
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 71
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 72
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 73
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 74
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 75
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 76
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 77
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 78
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 79
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 80
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 81
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 82
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 83
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 84
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 85
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 86
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 87
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 88
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 89
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 90
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 91
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 92
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 93
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 94
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 95
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 96
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 97
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 98
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 99
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 100
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 101
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 102
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 103
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 104
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 105
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 106
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 107
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 108
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 109
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 110
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 111
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 112
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 113
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 114
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 115
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 116
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 117
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 118
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 119
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 120
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 121
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 122
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 123
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 124
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 125
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 126
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 127
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 128
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 129
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 130
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 131
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 132
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 133
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 134
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 135
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 136
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 137
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 138
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 139
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 140
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 141
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 142
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 143
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 144
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 145
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 146
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 147
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 148
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 149
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 150
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 151
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 152
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 153
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 154
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 155
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 156
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 157
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 158
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 159
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 160
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 161
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 162
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 163
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 164
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 165
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 166
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 167
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 168
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 169
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 170
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 171
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 172
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 173
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 174
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 175
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 176
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 177
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 178
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 179
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 180
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 181
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 182
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 183
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 184
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 185
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 186
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 187
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 188
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 189
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 190
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 191
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 192
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 193
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 194
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 195
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 196
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 197
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 198
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 199
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | 200