## Calculator & Graphs
Prediction Analysis Calculator | [7 empty] | Improvement Profile
C | TSPI | SPI(t) | Threshold | ED | IEAC(t) | ED/PD | PD | AT | SPI(t) | Instruction
0.15385 | 1.1 | 0.66667 | 1.1 | 20 | 30 | 1 | 20 | NA | NA
0.001 | 1.0005 | 0.66667 | 1.1 | [6 empty] | Enter values for AT, ES, PD, and ED into the tan cells. The values for AT, ES, PD,
0.1 | 1.0588 | 0.66667 | 1.1 |  | ES = | 10 |  |  |  | and ED are in consistent units of time. Calculated values for TSPI will display in
0.2 | 1.1429 | 0.66667 | 1.1 |  | AT = | 15 |  |  |  | column B. Where TSPI exceeds the threshold of 1.100 indicates the point at which
0.3 | 1.2727 | 0.66667 | 1.1 | Improvement Period = |  | 0 |  |  |  | recovery and achievement of ED becomes extremely unlikely. A negative value
0.4 | 1.5 | 0.66667 | 1.1 | [6 empty] | for TSPI is an indication that ED is exceeded at the corresponding schedule
0.5 | 2 | 0.66667 | 1.1 |  | Window = | Not Likely |  |  |  | fraction complete (C = ES/PD) of the project. The value of C (< 1) at which TSPI
0.6 | 4 | 0.66667 | 1.1 |  |  |  | % Change |  |  | equals the threshold value, 1.100, is displayed in the gold colored cell in the C
0.7 | -6 | 0.66667 | 1.1 |  | TSPI = | 2 | 200% |  |  | column. The opportunity for project recovery, as a fraction of PD, is in the cell at
0.8 | -1 | 0.66667 | 1.1 |  | SPI(t)r = | NA | NA |  |  | the right of "Window =." Other than C, abbreviations are from ES terminology.
0.9 | -0.28571 | 0.66667 | 1.1 |  | Numerator = | NA | IP Rate
0.999 | -0.002006 | 0.66667 | 1.1 |  | Denominator = | NA | NA |  |  | Enter the number of periods over which improvement is to be made into cell H7.
When the number of periods is too large, the cell displays red. The improvement is
from the current SPI(t) value in cell C3 to the TSPI value indicated in cell H11. The
TSPI value is the efficiency needed for the remainder of the project to complete at
the ED entered. SPI(t)r is the efficiency after accounting for the improvement period.
Evaluate the % Change values and Improvement Profile (IP Rate) as to the likelihood
the improvement is achievable. Generally, realizing an efficiency increase > 50% is
not considered probable. An IP Rate < 10% is desirable, as well.
The calculator may be used to determine an achievable duration by changing the
values of ED and Improvement Period, and then re-evaluating the % Change
and IP Rate numbers.
Note: Historically, it has been assumed that improvement in performance efficiency
is not possible when the increase exceeds 10%. However, there is evidence that
recovery is possible, as long as TSPI has not exceeded the threshold, 1.10.
Certainly, a lower value for % Change makes it more likely the project can be
recovered to ED.
.

## Description
Description
Two graphs are shown on the Calculator & Graphs sheet. The graphs use different y-axis scaling.
The graph on the left has a scale for the SPI(t) index beginning at 0.7 and concluding at 1.3. The
graph on the right has considerably larger range, from -4.0 to + 8.0.
The two graphs are useful for different purposes. The graph on the right provides an overview of the
behavior of TSPI. With the example settings of SPI(t) = 0.667 and ED = 25, i.e. ED (estimated
duration) with PD = 20, the general behavior is shown. Obviously SPI(t) is a value of schedule
performance which cannot achieve the ED. As the fraction complete increases, the TSPI will first
increase to a high positive value. After reaching a peak positive value, TSPI rapidly decreases and
becomes negative. As the fraction complete approaches 1.0, TSPI approaches zero and concludes
at 0.0 when C = 1.0. Having a negative value for TSPI indicates a requirement for additional
duration; without added time, the project will complete at an actual duration in excess of ED.
The graph on the left provides a more detailed view of the TSPI behavior. It can be seen from this
view that there is good reason for the TSPI "rule of thumb": When TSPI exceeds the value of 1.1 it
is unlikely that the project can recover and complete within the ED. From research, it appears to
be a reliable indication that the project is "out of control." As can be observed, the positive change
in TSPI with increasing fraction complete (C) rapidly accelerates after reaching the 1.1 value.
The left graph clearly shows the point at which TSPI exceeds the threshold of 1.1. Being able to
observe this crossing is useful in that a project manager can make a determination of the project's
chance for successful completion within the desired or estimated duration. For example, using
ES = 10, At = 15, PD = 20, and ED = 25, when the project is 70 percent complete TSPI = 1.50.
Recovery is possible to achieve the ED, but extremely unlikely.
A more sophisticated use of the calculator is the evaluation for having a successful schedule
recovery. For the example entries, TSPI = 1.000 must be achieved for the remainder of the project.
At the very beginning of AT = 16, the schedule performance efficiency must increase from 0.667
to 1.000, a 50% instantaneous increase. The example allows an improvement time of 7 periods. The
recovery performance efficiency, SPI(t)r, must then increase to 1.179 by period 22, as observed in
the Improvement Profile. The percent change from SPI(t) @ AT = 15 to SPI(t)r @ AT = 22 is an
increase of 76.9%. An increase in performance efficiency this large is not very likely.
An achievable recovery may be assessed by adjusting ED and the improvement period (IP). As
well, the Improvement Profile should be assessed as to whether the rate of performance increase is
doable. For example, increase ED to 27. Leaving IP = 7, the efficiency percent change is reduced
to 35.3%, while the needed improvement/period (IP Rate) decreased from 11% to 5%. Thus, with
the positive change to both, % Change and IP Rate, ED = 27 is considered to be an achievable
project duration.
The calculator may be used for cost analysis as well. Change the headings using the following
substitutions: TCPI for TSPI, CPI for SPI(t), BAC for PD, EAC for ED, EV for ES, and AC for AT.
As well, change the graph titles to TCPI. The method of application and interpretation is identical to
that described for TSPI.

## Derivation SPI(t)r
Derivation of SPI(t)r
T = TSPI | [5 empty] | Area T
Area T = T x (1.00 - C1)
C1 | [8 empty] | 1
|  |  |  | R = SPI(t)r |  |  |  | Area 3 |  | Area 3 = (R - S) x (1 - C2)
Area 2
[10 empty] | Area 2 = (R - S)/2 x (C2 - C1) | (assuming linear improvement from C1 to C2)
S = SPI(t) | [5 empty] | Area 1
Area 1 = S x (1.00 - C1)
C1 |  |  |  | C2 |  |  |  |  | 1
Derivation:
Area T = Area 1 + Area 2 + Area 3
Adding Areas 2 & 3: (R - S) x [(C2 - C1)/2 + (1 - C2)] = (R - S) x [1 - (C1 + C2)/2]
|  | Thus, | T x (1.00 - C1) = S x (1.00 - C1) + (R - S) x [1 - (C1 + C2)/2]
(T - S) x (1.00 - C1) = (R - S) x [1 - (C1 + C2)/2]
| Solve for R |  | R = (T - S) x [(1 - C1) / (1 - (C1 + C2)/2 ] + S
| Improvement Period |  | P = C2 - C1
| Express R using P |  | R = (T - S) x [(1 - C1) / (1 - C1 - P/2) ] + S |  |  |  | where P is at the same scale of C1 and C2 (…# improvement periods divided by ED)
Express using ED, AT, & P |  |  | R= (T - S) x [(ED - AT) / (ED - AT - P/2)] + S |  |  |  | where P is the number of improvement periods