## Data Input & Results
Probability of Recovery Calculator
EVM & ES Data Input
AT | EV | AC | ES | BAC | TAB | PD | TD | Instructions for Use
Enter the EVM & ES (or ES(L)C) data as they are known into the tan colored cells. | bar: AT; EVM & ES Data Input BAC to EVM & ES Data Input TD
AT: 2 | BAC, TAB, PD, and TD must be entered with the first data entry. Enter a value in the range 0.0 - 0.2 for Unstable Period.
AT: 3; EVM & ES Data Input TAB: TSPI > 1.10; EVM & ES Data Input PD: S-Period; EVM & ES Data Input TD: ES% | The current recovery probabilities are shown below with the period of opportunity windows computed and
AT: 4 | displayed at the left. The analysis of the computed results is discussed in the section, "Interpretation of Results."
5 |  |  |  |  | ES%cur | ES%T | S-Window
6
AT: 7 |  | Probability of Recovery
8 |  |  |  |  | TCPI > 1.10 | C-Period | EV%
AT: 9 |  | Probability-Schedule | Probability-Cost
10 |  |  |  |  | EV%cur | EV%T | C-Window
11
12
13 |  |  |  |  | Unstable Period (0.0 - 0.2) |  | 0.15
14
15
16
17 |  |  |  |  | Interpretation of Results
18
AT: 19; EVM & ES Data Input TAB: TSPI > 1.10 | S-Period |  |  | ES%
AT: 20; EVM & ES Data Input TAB: The value of the 1st TSPI value > 1.10 after ES% ³ 0.0 - 0.2 | The performance period number at which TSPI > 1.10 occurs |  |  | Percent complete of the PD when TSPI > 1.10 occurs
AT: 21; EVM & ES Data Input TAB: ES%cur | ES%T |  |  | S-Window
AT: 22; EVM & ES Data Input TAB: Current percent complete of planned duration (PD) | Percent of PD for when TSPI = 1.10 using current SPI(t)c |  |  | The portion of the PD in which there is opportunity to recover
23
AT: 24; EVM & ES Data Input TAB: TCPI > 1.10 | C-Period |  |  | EV%
AT: 25; EVM & ES Data Input TAB: The value of the 1st TCPI value > 1.10 after EV% ³ 0.0 - 0.2 | The performance period number at which TCPI > 1.10 occurs |  |  | Percent complete of the BAC when TCPI > 1.10 occurs
AT: 26; EVM & ES Data Input TAB: EV%cur | EV%T |  |  | C-Window
AT: 27; EVM & ES Data Input TAB: Current percent complete of budget at completion (BAC) | Percent of BAC for when TCPI = 1.10 using current CPIc |  |  | The portion of BAC in which there is opportunity to recover
28
29 |  |  |  | . | The project manager's objective is to have S-Window and C-Window showing "Likely." When "Likely" appears, the project is performing such that if current performance continues, it will
30 |  |  |  |  | complete within the total duration (TD) and total allocated budget (TAB). When "Likely" is indicated, the value displayed for Probability of Recovery (POR) will be very high, and often will equal
31 |  |  |  |  | 100%. Conversely, when the value for S- or C-Window is "Not Likely", the POR value will be low, approaching 0.00. The combination of "Not Likely" and a very low value for POR is strong
32 |  |  |  |  | indication that additional funding and/or duration is required to achieve the project requirements.
33 |  |  |  |  | Between the two extremes is the area where recovery is possible. When recovery is possible, the paired values, S-Window with Probability-Schedule and C-Window with Probability-Cost, are
34 |  |  |  |  | used in the decision to take management action. The goal of recovery is to improve performance such that the project completes within the TD and TAB constraints.
35
36
37 |  |  |  |  | Notes:
38 |  |  |  |  | 1. The results for S- and C-Window and Probability -Schedule and -Cost will show as "Indeterminate" until the project has progressed to the value entered for the Unstable Period.
39 |  |  |  |  | 2. Applying Earned Schedule-Longest Path, i.e. using ES(L)C instead of ES, will yield significantly improved results for schedule performance analysis. For more information concerning ES(L)C,
40 |  |  |  |  | reference the Example ES(L) Analysis sheet of the ES-LP calculator.
41
42
43
44
45
46
47
48
49
50

## Prob Sched
Probability of Recovery - Schedule
AT | ES | SPI(t)C | SPI(t)P | ln SPI(t)C | ln SPI(t)P | S lnp^2 | S -2p*c | i * lnc^2 | Variation | s | sM | AFS | sM * AFS | NumT | DenomT | SPI(t)T | ln SPI(t)T | t-Score | PRcv | Current PRcv | Count PRcv | PD | TD | TD/PD | TSPI | >1.10 | Yes # | P-Cond
1 | 0 | [19 empty] | 0 | 0 | 0
2 | 0 | [17 empty] | #N/A
3 | 0 | [17 empty] | #N/A
4 | 0 | [17 empty] | #N/A
5 | 0 | [17 empty] | #N/A
6 | 0 | [17 empty] | #N/A
7 | 0 | [17 empty] | #N/A
8 | 0 | [17 empty] | #N/A
9 | 0 | [17 empty] | #N/A
10 | 0 | [17 empty] | #N/A
11 | 0 | [17 empty] | #N/A
12 | 0 | [17 empty] | #N/A
13 | 0 | [17 empty] | #N/A
14 | 0 | [17 empty] | #N/A
15 | 0 | [17 empty] | #N/A
16 | 0 | [17 empty] | #N/A
17 | 0 | [17 empty] | #N/A
18 | 0 | [17 empty] | #N/A
19 | 0 | [17 empty] | #N/A
20 | 0 | [17 empty] | #N/A | TSPI > 1.10 | Period | ES%
21 | 0 | [17 empty] | #N/A
22 | 0 | [17 empty] | #N/A | ES%cur | ES%T | Window | #Entries
23 | 0 | [17 empty] | #N/A |  |  |  | 0
24 | 0 | [17 empty] | #N/A |  | #VALUE!
25 | 0 | [17 empty] | #N/A
26 | 0 | [17 empty] | #N/A
27 | 0 | [17 empty] | #N/A | Unstable Period (0.0 - 0.2) |  | 0.15
28 | 0 | [17 empty] | #N/A
29 | 0 | [17 empty] | #N/A
30 | 0 | [17 empty] | #N/A
31 | 0 | [17 empty] | #N/A
32 | 0 | [17 empty] | #N/A
33 | 0 | [17 empty] | #N/A
34 | 0 | [17 empty] | #N/A
35 | 0 | [17 empty] | #N/A
36 | 0 | [17 empty] | #N/A
37 | 0 | [17 empty] | #N/A
38 | 0 | [17 empty] | #N/A
39 | 0 | [17 empty] | #N/A
40 | 0 | [17 empty] | #N/A
41 | 0 | [17 empty] | #N/A
42 | 0 | [17 empty] | #N/A
43 | 0 | [17 empty] | #N/A
44 | 0 | [17 empty] | #N/A
45 | 0 | [17 empty] | #N/A
46 | 0 | [17 empty] | #N/A
47 | 0 | [17 empty] | #N/A
48 | 0 | [17 empty] | #N/A
49 | 0 | [17 empty] | #N/A
50 | 0 | [17 empty] | #N/A

## Prob Cost
Probability of Recovery - Cost
AT | EV | AC | CPI(t)C | CPI(t)P | ln CPI(t)C | ln CPI(t)P | S lnp^2 | S -2p*c | i * lnc^2 | Variation | s | sM | AFS | sM * AFC | NumT | DenomT | CPI(t)T | ln CPI(t)T | t-Score | PRcv | Current PRcv | Count PRcv | BAC | TAB | TAB/BAC | TCPI | >1.10 | Yes # | P-Cond
1 | 0 | 0 | [19 empty] | 0 | 0 | 0
2 | 0 | 0 | [17 empty] | #N/A
3 | 0 | 0 | [17 empty] | #N/A
4 | 0 | 0 | [17 empty] | #N/A
5 | 0 | 0 | [17 empty] | #N/A
6 | 0 | 0 | [17 empty] | #N/A
7 | 0 | 0 | [17 empty] | #N/A
8 | 0 | 0 | [17 empty] | #N/A
9 | 0 | 0 | [17 empty] | #N/A
10 | 0 | 0 | [17 empty] | #N/A
11 | 0 | 0 | [17 empty] | #N/A
12 | 0 | 0 | [17 empty] | #N/A
13 | 0 | 0 | [17 empty] | #N/A
14 | 0 | 0 | [17 empty] | #N/A
15 | 0 | 0 | [17 empty] | #N/A
16 | 0 | 0 | [17 empty] | #N/A
17 | 0 | 0 | [17 empty] | #N/A
18 | 0 | 0 | [17 empty] | #N/A
19 | 0 | 0 | [17 empty] | #N/A
20 | 0 | 0 | [17 empty] | #N/A | TCPI > 1.10 | Period | EV%
21 | 0 | 0 | [17 empty] | #N/A
22 | 0 | 0 | [17 empty] | #N/A | EV%cur | EV%T | Window | #Entries
23 | 0 | 0 | [17 empty] | #N/A |  |  |  | 0
24 | 0 | 0 | [17 empty] | #N/A |  | #VALUE!
25 | 0 | 0 | [17 empty] | #N/A
26 | 0 | 0 | [17 empty] | #N/A
27 | 0 | 0 | [17 empty] | #N/A | Unstable Period (0.0 - 0.2) |  | 0.15
28 | 0 | 0 | [17 empty] | #N/A
29 | 0 | 0 | [17 empty] | #N/A
30 | 0 | 0 | [17 empty] | #N/A
31 | 0 | 0 | [17 empty] | #N/A
32 | 0 | 0 | [17 empty] | #N/A
33 | 0 | 0 | [17 empty] | #N/A
34 | 0 | 0 | [17 empty] | #N/A
35 | 0 | 0 | [17 empty] | #N/A
36 | 0 | 0 | [17 empty] | #N/A
37 | 0 | 0 | [17 empty] | #N/A
38 | 0 | 0 | [17 empty] | #N/A
39 | 0 | 0 | [17 empty] | #N/A
40 | 0 | 0 | [17 empty] | #N/A
41 | 0 | 0 | [17 empty] | #N/A
42 | 0 | 0 | [17 empty] | #N/A
43 | 0 | 0 | [17 empty] | #N/A
44 | 0 | 0 | [17 empty] | #N/A
45 | 0 | 0 | [17 empty] | #N/A
46 | 0 | 0 | [17 empty] | #N/A
47 | 0 | 0 | [17 empty] | #N/A
48 | 0 | 0 | [17 empty] | #N/A
49 | 0 | 0 | [17 empty] | #N/A
50 | 0 | 0 | [17 empty] | #N/A
From Input Data Sheet
BAC
TAB
TAB/BAC

## Example Data
EVM & ES Data Input
AT | EV | AC | ES | BAC | TAB | PD | TD
1 | 927.7251 | 1605.75 | 0.30689 | 38140 | 38140 | 21 | 21
2 | 1903.9897 | 2766.25 | 0.62983
3 | 2466.7675 | 4324.25 | 0.816
4 | 3413.917 | 6137.5 | 1.1573 |  | Note: The graphs and probability of recovery
5 | 4471.5522 | 7887.5 | 1.5829 |  | are computed having no reserves for cost or
6 | 7151.8043 | 9835 | 2.7085 |  | or schedule. A suggestion to increase
7 | 7476.3148 | 10135 | 2.8484 |  | familiarity with the calculator is to increase
8 | 9271.8174 | 13216.75 | 3.636 |  | TAB and TD, i.e. adding in reserves. The
9 | 11441.0396 | 14755 | 4.652 |  | effect of increasing reserves can be
10 | 13301.7187 | 16656.25 | 5.6379 |  | observed. As well, reduce the number of
11 | 14699.4751 | 18767.75 | 7.2862 |  | data input for EV, AC, and ES. The values
12 | 15985.2442 | 20896.75 | 8.0265 |  | produced for Probability of Recovery are for
13 | 16752.7236 | 23364 | 8.4163 |  | an intermediate status point.
14 | 17077.4609 | 23663.75 | 8.5812
15 | 20317.8224 | 26651 | 10.1565
16 | 23060.7878 | 28436.5 | 11.4104
17 | 26587.8806 | 30407.5 | 13.7856
18 | 28681.1878 | 32012 | 15.0146
19 | 30134.9703 | 33999.75 | 15.6353
20 | 31487.4931 | 35554 | 16.243
21 | 32526.2873 | 37110.5 | 16.7495
22 | 33504.3992 | 38468.25 | 17.2485
23 | 34512.89 | 39798.25 | 17.7881
24 | 36488.7326 | 41155.25 | 18.8776
25 | 37629.8127 | 42600.25 | 19.7045
AT: 26; EVM & ES Data Input EV: 38140; EVM & ES Data Input AC: 43983; EVM & ES Data Input ES: 21 | Probability of Recovery
[8 empty] | Probability-Schedule |  | Probability-Cost
[9 empty] | 0% |  | 0%