## Instruction
Rework Calculation Instruction
The p-factor derived from ES provides information about schedule adherence. However, due to the inherent
behavior of P, a manager cannot determine whether his/her actions have had an effect on the SA of the
project. Recall that P increases in value and concludes at the value of 1.0 at project completion, regardless of
efforts by managers and workers to cause improvement. By normalizing the potential rework to remaining
work, the efforts of the project team become visible. Trending can be observed and used for project control.
Significantly, the normalized value indicates the relationship of the additional work (rework) to the remaining
project work, thereby providing management impetus to make improvement.
The Schedule Adherence Index (SAI) is defined as the potential value of rework identified by the Earned
Schedule (ES) p-factor (P) at status point n divided by the work remaining:
SAI = (1 - P) · EV · f(r) / (BAC - EV)
where f(r) is the fraction of the out of sequence EV which requires rework
and | f(r ) = 1 - C · e^(-0.5 · (1 - C))
where C = EV / BAC
By monitoring the value of SAI throughout project execution a manager can enhance his/her understanding
of schedule adherence (SA) performance.
The SAI indicator is interpreted as follows:
1) SAI is the amount of additional work, i.e. rework, caused by poor SA in
relation to the planned project work remaining. An SAI value in excess of
0.10 indicates a need for improvement. General areas for investigation are
lack of process discipline, poor planning, poor management, and external
schedule pressures.
2) When the SAI trend is increasing, SA is becoming worse and conversely
when the trend is decreasing, SA is improving.
Computed rework values are available by performance period, cumulative to date, and the forecast by period.
The total forecast cost for rework attributable to lack of SA is available for comparison to both the BAC and
Final Cost. The total forecast is computed using an approximate integration of the SAI graph.
The worksheet, EV(r) Accrual, calculates an estimate of the out of sequence work for which accomplishment
is claimed. As will be observed, the value is somewhat larger than the rework forecast. Knowing the
quantity, may cause management to be more aware of schedule performance discipline and the potential
waste in the execution of the project. The calculations on this sheet are linked to the data entry and
calculations made on the SAI & Rework Calculation sheet.
Application Notes
1) To use the spreadsheet requires periodic amounts of EV(cumulative), the corresponding p-factor
values, and the value for BAC.
2) Enter the EV(cum), P values and BAC into the appropriate cells on the SAI calculation worksheet. The
calculations are made within the spreadsheet and linked to the SAI Graph and Forecast Graph sheets.
3) Generally, the y-axis scaling on the SAI & Forecast graph and Rework & EV(r ) Accrual graph will require
adjustment to obtain the best appearance.
4) To clear the SAI & Rework Calculation spreadsheet, copy #N/A into the cells having data for EV and P.
Likewise enter #N/A into the cell for the value of BAC. Doing this causes the graphs to be cleared as well.
Duration Increase Forecast Instruction
The duration increase is the forecast at project completion of the additive periods attributed to rework from
out of sequence performance.
The sheet is linked to the SAI & Rework Calculation sheet. It is very simple to use. Enter the Planned
Duration (PD) and the SPI(t) values from each status period, as they occur. The computed results will appear
in the Duration Increase% and Duration Increase (DI) rows. The unit value for Duration Increase is in periods.
Thus, the unit measure of the status period (e.g,, month, week, day) determines the interpretation of the
number in the DI row.
The forecast model is limited in the range of application to the following conditions: SPI(t) less than 1.74776
and Rework% less than or equal to 20%. When a value is input that is outside of the range, "Void" appears
in the Duration Increase row.

## SAI & Rework Calculation
Schedule Adherence Index & Rework Estimate
BAC | 170
Measures | Status Point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
| EV | 9.85 | 11.2 | 14.35 | 15.25 | 19.1 | 24.4833 | 36.2167 | 40 | 50.0667 | 53.5 | 59.2333 | 74.5 | 78.2333 | 97.4 | 101.5333 | 104.7167 | 124.25 | 128.9333 | 134.3667 | 138.95 | 143.2 | 145.45 | 146 | 147.9 | 153.75 | 157.5 | 158.75 | 160.9 | 165 | 165.2 | 165.4 | 166.5 | 166.7 | 167.8 | 168 | 170 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| P | 0.66723 | 0.75198 | 0.78552 | 0.78506 | 0.92728 | 0.93673 | 0.78552 | 0.76072 | 0.84587 | 0.88294 | 0.8535 | 0.8255 | 0.84511 | 0.87921 | 0.88297 | 0.89181 | 0.92854 | 0.95328 | 0.95871 | 0.97198 | 0.96865 | 0.9766 | 0.97782 | 0.98363 | 0.983 | 0.99265 | 0.99514 | 1 | 0.98701 | 0.98755 | 0.98808 | 0.99099 | 0.99152 | 0.99183 | 0.99209 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Calculations | C | 0.057941 | 0.065882 | 0.084412 | 0.089706 | 0.11235 | 0.14402 | 0.21304 | 0.23529 | 0.29451 | 0.31471 | 0.34843 | 0.43824 | 0.4602 | 0.57294 | 0.59725 | 0.61598 | 0.73088 | 0.75843 | 0.79039 | 0.81735 | 0.84235 | 0.85559 | 0.85882 | 0.87 | 0.90441 | 0.92647 | 0.93382 | 0.94647 | 0.97059 | 0.97176 | 0.97294 | 0.97941 | 0.98059 | 0.98706 | 0.98824 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| f(r) | 0.96382 | 0.9587 | 0.94659 | 0.94309 | 0.92792 | 0.90613 | 0.85626 | 0.83947 | 0.79303 | 0.77659 | 0.74845 | 0.66908 | 0.64866 | 0.53722 | 0.51168 | 0.49163 | 0.36113 | 0.32786 | 0.28825 | 0.25398 | 0.22149 | 0.20401 | 0.19971 | 0.18475 | 0.1378 | 0.10697 | 0.096569 | 0.078525 | 0.043581 | 0.041858 | 0.040133 | 0.030619 | 0.028883 | 0.019307 | 0.017561 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| EV(r) | 3.2778 | 2.7778 | 3.0778 | 3.2778 | 1.3889 | 1.5492 | 7.7678 | 9.5712 | 7.7169 | 6.2627 | 8.678 | 13 | 12.1176 | 11.7647 | 11.8824 | 11.3294 | 8.8794 | 6.0241 | 5.5483 | 3.8931 | 4.4897 | 3.4034 | 3.2379 | 2.4207 | 2.6143 | 1.1571 | 0.77143 | 0 | 2.1429 | 2.0571 | 1.9714 | 1.5 | 1.4143 | 1.3714 | 1.3286 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| BAC - EV | 160.15 | 158.8 | 155.65 | 154.75 | 150.9 | 145.5167 | 133.7833 | 130 | 119.9333 | 116.5 | 110.7667 | 95.5 | 91.7667 | 72.6 | 68.4667 | 65.2833 | 45.75 | 41.0667 | 35.6333 | 31.05 | 26.8 | 24.55 | 24 | 22.1 | 16.25 | 12.5 | 11.25 | 9.1 | 5 | 4.8 | 4.6 | 3.5 | 3.3 | 2.2 | 2 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
SA Index | SAI | 0.019727 | 0.01677 | 0.018718 | 0.019976 | 0.0085406 | 0.0096465 | 0.049717 | 0.061806 | 0.051027 | 0.041747 | 0.058637 | 0.091079 | 0.085655 | 0.087055 | 0.088802 | 0.085319 | 0.070091 | 0.048094 | 0.044882 | 0.031845 | 0.037106 | 0.028283 | 0.026944 | 0.020236 | 0.022169 | 0.0099026 | 0.0066219 | 0 | 0.018677 | 0.017939 | 0.0172 | 0.013122 | 0.012379 | 0.012036 | 0.011665 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Rework | By Period | 0.097153 | 0.024635 | 0.055893 | 0.017412 | 0.054894 | 0.048954 | 0.34826 | 0.21096 | 0.56792 | 0.15926 | 0.28777 | 1.1428 | 0.3299 | 1.6551 | 0.36344 | 0.27714 | 1.5178 | 0.27675 | 0.25259 | 0.17583 | 0.14652 | 0.073562 | 0.015187 | 0.044821 | 0.12403 | 0.060134 | 0.010328 | 0.0071185 | 0.038289 | 0.0036617 | 0.0035139 | 0.016677 | 0.0025501 | 0.013428 | 0.0023701 | 0.011665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative | 0.097153 | 0.12179 | 0.17768 | 0.19509 | 0.24999 | 0.29894 | 0.6472 | 0.85817 | 1.4261 | 1.5854 | 1.8731 | 3.0159 | 3.3459 | 5.001 | 5.3644 | 5.6416 | 7.1594 | 7.4362 | 7.6887 | 7.8646 | 8.0111 | 8.0847 | 8.0998 | 8.1447 | 8.2687 | 8.3288 | 8.3392 | 8.3463 | 8.3846 | 8.3882 | 8.3917 | 8.4084 | 8.411 | 8.4244 | 8.4268 | 8.4384 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Forecast | 3.2564 | 2.7848 | 3.0911 | 3.2863 | 1.5388 | 1.7027 | 7.2985 | 8.8929 | 7.5459 | 6.4489 | 8.3681 | 11.714 | 11.2061 | 11.3212 | 11.4444 | 11.2115 | 10.3661 | 9.4112 | 9.288 | 8.8534 | 9.0055 | 8.779 | 8.7465 | 8.5919 | 8.6289 | 8.4526 | 8.4137 | 8.3463 | 8.478 | 8.4743 | 8.4709 | 8.4544 | 8.4518 | 8.4509 | 8.4501 | 8.4384 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## SAI & Forecast Graph
Status Point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Percent Complete | 0.057941 | 0.065882 | 0.084412 | 0.089706 | 0.11235 | 0.14402 | 0.21304 | 0.23529 | 0.29451 | 0.31471 | 0.34843 | 0.43824 | 0.4602 | 0.57294 | 0.59725 | 0.61598 | 0.73088 | 0.75843 | 0.79039 | 0.81735 | 0.84235 | 0.85559 | 0.85882 | 0.87 | 0.90441 | 0.92647 | 0.93382 | 0.94647 | 0.97059 | 0.97176 | 0.97294 | 0.97941 | 0.98059 | 0.98706 | 0.98824 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
SA Index | 0.019727 | 0.01677 | 0.018718 | 0.019976 | 0.0085406 | 0.0096465 | 0.049717 | 0.061806 | 0.051027 | 0.041747 | 0.058637 | 0.091079 | 0.085655 | 0.087055 | 0.088802 | 0.085319 | 0.070091 | 0.048094 | 0.044882 | 0.031845 | 0.037106 | 0.028283 | 0.026944 | 0.020236 | 0.022169 | 0.0099026 | 0.0066219 | 0 | 0.018677 | 0.017939 | 0.0172 | 0.013122 | 0.012379 | 0.012036 | 0.011665 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Rework Forecast | 3.2564 | 2.7848 | 3.0911 | 3.2863 | 1.5388 | 1.7027 | 7.2985 | 8.8929 | 7.5459 | 6.4489 | 8.3681 | 11.714 | 11.2061 | 11.3212 | 11.4444 | 11.2115 | 10.3661 | 9.4112 | 9.288 | 8.8534 | 9.0055 | 8.779 | 8.7465 | 8.5919 | 8.6289 | 8.4526 | 8.4137 | 8.3463 | 8.478 | 8.4743 | 8.4709 | 8.4544 | 8.4518 | 8.4509 | 8.4501 | 8.4384 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## EV(r) Accrual
EV(r) Accumulation Estimate
BAC | 170
Measures | Status Point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
| EV | 9.85 | 11.2 | 14.35 | 15.25 | 19.1 | 24.4833 | 36.2167 | 40 | 50.0667 | 53.5 | 59.2333 | 74.5 | 78.2333 | 97.4 | 101.5333 | 104.7167 | 124.25 | 128.9333 | 134.3667 | 138.95 | 143.2 | 145.45 | 146 | 147.9 | 153.75 | 157.5 | 158.75 | 160.9 | 165 | 165.2 | 165.4 | 166.5 | 166.7 | 167.8 | 168 | 170 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| P | 0.66723 | 0.75198 | 0.78552 | 0.78506 | 0.92728 | 0.93673 | 0.78552 | 0.76072 | 0.84587 | 0.88294 | 0.8535 | 0.8255 | 0.84511 | 0.87921 | 0.88297 | 0.89181 | 0.92854 | 0.95328 | 0.95871 | 0.97198 | 0.96865 | 0.9766 | 0.97782 | 0.98363 | 0.983 | 0.99265 | 0.99514 | 1 | 0.98701 | 0.98755 | 0.98808 | 0.99099 | 0.99152 | 0.99183 | 0.99209 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Calculations | C | 0.057941 | 0.065882 | 0.084412 | 0.089706 | 0.11235 | 0.14402 | 0.21304 | 0.23529 | 0.29451 | 0.31471 | 0.34843 | 0.43824 | 0.4602 | 0.57294 | 0.59725 | 0.61598 | 0.73088 | 0.75843 | 0.79039 | 0.81735 | 0.84235 | 0.85559 | 0.85882 | 0.87 | 0.90441 | 0.92647 | 0.93382 | 0.94647 | 0.97059 | 0.97176 | 0.97294 | 0.97941 | 0.98059 | 0.98706 | 0.98824 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| EV(r) | 3.2778 | 2.7778 | 3.0778 | 3.2778 | 1.3889 | 1.5492 | 7.7678 | 9.5712 | 7.7169 | 6.2627 | 8.678 | 13 | 12.1176 | 11.7647 | 11.8824 | 11.3294 | 8.8794 | 6.0241 | 5.5483 | 3.8931 | 4.4897 | 3.4034 | 3.2379 | 2.4207 | 2.6143 | 1.1571 | 0.77143 | 0 | 2.1429 | 2.0571 | 1.9714 | 1.5 | 1.4143 | 1.3714 | 1.3286 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| EV(r) / EV | 0.33277 | 0.24802 | 0.21448 | 0.21494 | 0.072717 | 0.063274 | 0.21448 | 0.23928 | 0.15413 | 0.11706 | 0.1465 | 0.1745 | 0.15489 | 0.12079 | 0.11703 | 0.10819 | 0.071464 | 0.046723 | 0.041292 | 0.028018 | 0.031352 | 0.023399 | 0.022178 | 0.016367 | 0.017003 | 0.0073469 | 0.0048594 | 0 | 0.012987 | 0.012452 | 0.011919 | 0.009009 | 0.008484 | 0.008173 | 0.0079082 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
EV(r) Accrual | By Period | 1.6389 | 0.39203 | 0.72843 | 0.19324 | 0.55373 | 0.36604 | 1.6295 | 0.85836 | 1.9802 | 0.46555 | 0.75555 | 2.4503 | 0.61486 | 2.6419 | 0.49149 | 0.35848 | 1.7546 | 0.27675 | 0.23911 | 0.15884 | 0.12616 | 0.061596 | 0.012534 | 0.036617 | 0.097609 | 0.045657 | 0.007629 | 0.0052238 | 0.026623 | 0.0025439 | 0.0024372 | 0.01151 | 0.0017493 | 0.0091614 | 0.0016081 | 0.0079082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulation | 1.6389 | 2.0309 | 2.7593 | 2.9526 | 3.5063 | 3.8724 | 5.5019 | 6.3602 | 8.3404 | 8.8059 | 9.5615 | 12.0118 | 12.6267 | 15.2686 | 15.7601 | 16.1186 | 17.8732 | 18.1499 | 18.389 | 18.5479 | 18.674 | 18.7356 | 18.7482 | 18.7848 | 18.8824 | 18.9281 | 18.9357 | 18.9409 | 18.9675 | 18.9701 | 18.9725 | 18.984 | 18.9858 | 18.9949 | 18.9965 | 19.0045 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Rework & EV(r) Accrual Graph
Status Point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Percent Complete | 0.057941 | 0.065882 | 0.084412 | 0.089706 | 0.11235 | 0.14402 | 0.21304 | 0.23529 | 0.29451 | 0.31471 | 0.34843 | 0.43824 | 0.4602 | 0.57294 | 0.59725 | 0.61598 | 0.73088 | 0.75843 | 0.79039 | 0.81735 | 0.84235 | 0.85559 | 0.85882 | 0.87 | 0.90441 | 0.92647 | 0.93382 | 0.94647 | 0.97059 | 0.97176 | 0.97294 | 0.97941 | 0.98059 | 0.98706 | 0.98824 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Rework Cumulative | 0.097153 | 0.12179 | 0.17768 | 0.19509 | 0.24999 | 0.29894 | 0.6472 | 0.85817 | 1.4261 | 1.5854 | 1.8731 | 3.0159 | 3.3459 | 5.001 | 5.3644 | 5.6416 | 7.1594 | 7.4362 | 7.6887 | 7.8646 | 8.0111 | 8.0847 | 8.0998 | 8.1447 | 8.2687 | 8.3288 | 8.3392 | 8.3463 | 8.3846 | 8.3882 | 8.3917 | 8.4084 | 8.411 | 8.4244 | 8.4268 | 8.4384 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
EV(r ) Accrual | 1.6389 | 2.0309 | 2.7593 | 2.9526 | 3.5063 | 3.8724 | 5.5019 | 6.3602 | 8.3404 | 8.8059 | 9.5615 | 12.0118 | 12.6267 | 15.2686 | 15.7601 | 16.1186 | 17.8732 | 18.1499 | 18.389 | 18.5479 | 18.674 | 18.7356 | 18.7482 | 18.7848 | 18.8824 | 18.9281 | 18.9357 | 18.9409 | 18.9675 | 18.9701 | 18.9725 | 18.984 | 18.9858 | 18.9949 | 18.9965 | 19.0045 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Rework Example Data
This example demonstrates extremely poor schedule adherence.
BAC | 185
Measures | Status Point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
| EV | 1: 14; 2: 37; 3: 58; 4: 82; 5: 97; 6: 113; 7: 125; 8: 137; 9: 157; 10: 177; 11: 185
| P | 1: 0.081633; 2: 0.20849; 3: 0.24713; 4: 0.33689; 5: 0.37113; 6: 0.43142; 7: 0.52; 8: 0.64964; 9: 0.82166; 10: 0.9548; 11: 1
Trial Data 1 | bar: 1 to 12
This example demonstrates a project whose schedule adherence remains fairly consistent throughout the effort.
BAC | 1200
Measures | Status Point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
| EV | 1: 240; 2: 360; 3: 600; 4: 840; 5: 1080; 6: 1200
| P | 1: 0.2; 2: 0.5; 3: 0.7; 4: 0.82; 5: 0.87; 6: 1
Trial Data 2 | bar: 1 to 12
This example is real data from a good performing project, demonstrating high schedule adherence.
BAC | 2488202
Measures | Status Point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
| EV | 1: 549707.2484; 2: 668775.6161; 3: 784507.5244; 4: 881288.4291; 5: 986528.8752; 6: 1299880.2986; 7: 1422033.407; 8: 1526841.9662; 9: 1617975.7428; 10: 1716130; 11: 1826991; 12: 1930651; 13: 2015852; 14: 2088966.8047
| P | 1: 0.92977; 2: 0.91451; 3: 0.96302; 4: 0.96221; 5: 0.93897; 6: 0.95745; 7: 0.97531; 8: 0.97023; 9: 0.97544; 10: 0.9844; 11: 0.99423; 12: 0.99545; 13: 0.99582; 14: 0.99285
Trial Data 3 | bar: 1 to 12

## Duration Increase Forecast
********************************************************** Duration Increase Forecast Calculation **********************************************************
Status Point | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Percent Complete | 0.057941 | 0.065882 | 0.084412 | 0.089706 | 0.11235 | 0.14402 | 0.21304 | 0.23529 | 0.29451 | 0.31471 | 0.34843 | 0.43824 | 0.4602 | 0.57294 | 0.59725 | 0.61598 | 0.73088 | 0.75843 | 0.79039 | 0.81735 | 0.84235 | 0.85559 | 0.85882 | 0.87 | 0.90441 | 0.92647 | 0.93382 | 0.94647 | 0.97059 | 0.97176 | 0.97294 | 0.97941 | 0.98059 | 0.98706 | 0.98824 | 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Budget At Completion | 170
Rework Forecast% | 1.916% | 1.638% | 1.818% | 1.933% | 0.9052% | 1.002% | 4.293% | 5.231% | 4.439% | 3.793% | 4.922% | 6.891% | 6.592% | 6.66% | 6.732% | 6.595% | 6.098% | 5.536% | 5.464% | 5.208% | 5.297% | 5.164% | 5.145% | 5.054% | 5.076% | 4.972% | 4.949% | 4.91% | 4.987% | 4.985% | 4.983% | 4.973% | 4.972% | 4.971% | 4.971% | 4.964% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
SPI(t) | 0.5 | 0.75 | 0.799 | 0.843 | 1 | 0.92 | 0.904 | 0.683 | 0.97 | 1.08 | 0.86 | 0.895 | 0.92 | 0.91 | 0.72 | 1.1 | 0.94 | 0.83 | 0.866 | 0.912 | 0.955 | 0.977 | 0.885 | 0.973 | 0.902 | 1.1 | 1.03 | 0.976 | 0.777 | 0.899 | 0.908 | 0.911 | 0.966 | 1.054 | 1.033 | 0.944
Planned Duration | 30
Duration Increase% | 2.884% | 1.972% | 2.082% | 2.111% | 0.8168% | 1.001% | 4.372% | 6.722% | 4.166% | 3.057% | 5.274% | 7.091% | 6.585% | 6.733% | 8.35% | 5.155% | 5.944% | 6.131% | 5.814% | 5.253% | 5.068% | 4.803% | 5.357% | 4.725% | 5.181% | 3.887% | 4.287% | 4.573% | 5.842% | 5.106% | 5.05% | 5.022% | 4.69% | 4.162% | 4.288% | 4.815%
Duration Increase | 0.86531 | 0.59175 | 0.62456 | 0.63322 | 0.24504 | 0.30015 | 1.3115 | 2.0165 | 1.2499 | 0.9171 | 1.5821 | 2.1274 | 1.9755 | 2.0199 | 2.5049 | 1.5466 | 1.7832 | 1.8394 | 1.7441 | 1.5758 | 1.5204 | 1.441 | 1.6071 | 1.4176 | 1.5542 | 1.166 | 1.2861 | 1.3718 | 1.7527 | 1.5318 | 1.5149 | 1.5066 | 1.4071 | 1.2486 | 1.2863 | 1.4444
Slope | 0.023116 | 0.019769 | 0.021943 | 0.023329 | 0.010923 | 0.012087 | 0.051811 | 0.063129 | 0.053567 | 0.04578 | 0.059404 | 0.083156 | 0.07955 | 0.080367 | 0.081242 | 0.079588 | 0.073587 | 0.066809 | 0.065934 | 0.062848 | 0.063929 | 0.062321 | 0.06209 | 0.060992 | 0.061255 | 0.060004 | 0.059727 | 0.059249 | 0.060184 | 0.060158 | 0.060133 | 0.060016 | 0.059998 | 0.059991 | 0.059986 | 0.059903
Intercept | 0.040402 | 0.034552 | 0.038351 | 0.040774 | 0.019091 | 0.021125 | 0.090553 | 0.11033 | 0.093622 | 0.080012 | 0.10382 | 0.14534 | 0.13903 | 0.14046 | 0.14199 | 0.1391 | 0.12861 | 0.11677 | 0.11524 | 0.10984 | 0.11173 | 0.10892 | 0.10852 | 0.1066 | 0.10706 | 0.10487 | 0.10439 | 0.10355 | 0.10519 | 0.10514 | 0.1051 | 0.10489 | 0.10486 | 0.10485 | 0.10484 | 0.1047