## Project Data
Project Data
|  | Divisor |  | 1000
|  | Divisor Display |  | $ 000
|  | Weekly (W) / Monthly (M) |  | M
|  | Duration Multiplier |  | 30.42
| Title 1 | Example Project Analysis
Title 2a
Title 2b
Title 3
| Status Date | 2013-07-02
Periods
|  |  | Budget at Complete | 38140
|  |  | Project Start Date | 2013-01-01
|  |  | Planned Duration | 21
|  |  | Planned Completion Date | 2014-10-01 19:41
|  |  | Statistical Forecast Confidence Level % | 90%
|  |  | Final Cost | 43983
|  |  | Final Duration | 26
|  |  | Actual Completion Date | 2013-07-02
Legend
Input Data Cell for calculations
Input Data Cell for information
Calculated Data Cell (do not modify)
© Walt Lipke
© Kym Henderson

## Input Data Sheet
Example Project Analysis
Input Data Sheet
0
Period | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Planned Values cum | 0 | 3023 | 5508 | 7828 | 10098 | 12158 | 13951 | 14205 | 15933 | 17902 | 19967 | 22208 | 24286 | 26331 | 26658 | 28647 | 30989 | 33040 | 34909 | 36709 | 38016 | 38140 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Earned Value cum | 0 | 927.7251 | 1903.9897 | 2466.7675 | 3413.917 | 4471.5522 | 7151.8043 | 7476.3148 | 9271.8174 | 11441.0396 | 13301.7187 | 14699.4751 | 15985.2442 | 16752.7236 | 17077.4609 | 20317.8224 | 23060.7878 | 26587.8806 | 28681.1878 | 30134.9703 | 31487.4931 | 32526.2873 | 33504.3992 | 34512.89 | 36488.7326 | 37629.8127 | 38140 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Costs cum | 0 | 1605.75 | 2766.25 | 4324.25 | 6137.5 | 7887.5 | 9835 | 10135 | 13216.75 | 14755 | 16656.25 | 18767.75 | 20896.75 | 23364 | 23663.75 | 26651 | 28436.5 | 30407.5 | 32012 | 33999.75 | 35554 | 37110.5 | 38468.25 | 39798.25 | 41155.25 | 42600.25 | 43983 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Earned Schedule cum | 0 | 0.30689 | 0.62983 | 0.816 | 1.1573 | 1.5829 | 2.7085 | 2.8484 | 3.636 | 4.652 | 5.6379 | 7.2862 | 8.0265 | 8.4163 | 8.5812 | 10.1565 | 11.4104 | 13.7856 | 15.0146 | 15.6353 | 16.243 | 16.7495 | 17.2485 | 17.7881 | 18.8776 | 19.7045 | 21 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage Complete cum | 0% | 2.432% | 4.992% | 6.468% | 8.951% | 11.72% | 18.75% | 19.6% | 24.31% | 30% | 34.88% | 38.54% | 41.91% | 43.92% | 44.78% | 53.27% | 60.46% | 69.71% | 75.2% | 79.01% | 82.56% | 85.28% | 87.85% | 90.49% | 95.67% | 98.66% | 100% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Percentage Complete period | 0% | 2.432% | 2.56% | 1.476% | 2.483% | 2.773% | 7.027% | 0.8508% | 4.708% | 5.688% | 4.879% | 3.665% | 3.371% | 2.012% | 0.8514% | 8.496% | 7.192% | 9.248% | 5.488% | 3.812% | 3.546% | 2.724% | 2.565% | 2.644% | 5.18% | 2.992% | 1.338% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Sched Analysis - Period Remove | 0
Cost Analysis - Period Remove | 0

## Statistical Calculation
Cost and Schedule Forecast Using Statistical Methods Template
Period | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Cum Pct | 0% | 2.432% | 4.992% | 6.468% | 8.951% | 11.72% | 18.75% | 19.6% | 24.31% | 30% | 34.88% | 38.54% | 41.91% | 43.92% | 44.78% | 53.27% | 60.46% | 69.71% | 75.2% | 79.01% | 82.56% | 85.28% | 87.85% | 90.49% | 95.67% | 98.66% | 100% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Period Pct | 0% | 2.432% | 2.56% | 1.476% | 2.483% | 2.773% | 7.027% | 0.8508% | 4.708% | 5.688% | 4.879% | 3.665% | 3.371% | 2.012% | 0.8514% | 8.496% | 7.192% | 9.248% | 5.488% | 3.812% | 3.546% | 2.724% | 2.565% | 2.644% | 5.18% | 2.992% | 1.338% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
PVc | 0 | 3023 | 5508 | 7828 | 10098 | 12158 | 13951 | 14205 | 15933 | 17902 | 19967 | 22208 | 24286 | 26331 | 26658 | 28647 | 30989 | 33040 | 34909 | 36709 | 38016 | 38140 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
EVc | 0 | 927.7251 | 1903.9897 | 2466.7675 | 3413.917 | 4471.5522 | 7151.8043 | 7476.3148 | 9271.8174 | 11441.0396 | 13301.7187 | 14699.4751 | 15985.2442 | 16752.7236 | 17077.4609 | 20317.8224 | 23060.7878 | 26587.8806 | 28681.1878 | 30134.9703 | 31487.4931 | 32526.2873 | 33504.3992 | 34512.89 | 36488.7326 | 37629.8127 | 38140 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ACc | 0 | 1605.75 | 2766.25 | 4324.25 | 6137.5 | 7887.5 | 9835 | 10135 | 13216.75 | 14755 | 16656.25 | 18767.75 | 20896.75 | 23364 | 23663.75 | 26651 | 28436.5 | 30407.5 | 32012 | 33999.75 | 35554 | 37110.5 | 38468.25 | 39798.25 | 41155.25 | 42600.25 | 43983 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ESc | 0 | 0.30689 | 0.62983 | 0.816 | 1.1573 | 1.5829 | 2.7085 | 2.8484 | 3.636 | 4.652 | 5.6379 | 7.2862 | 8.0265 | 8.4163 | 8.5812 | 10.1565 | 11.4104 | 13.7856 | 15.0146 | 15.6353 | 16.243 | 16.7495 | 17.2485 | 17.7881 | 18.8776 | 19.7045 | 21 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
PVp | 0 | 3023 | 2485 | 2320 | 2270 | 2060 | 1793 | 254 | 1728 | 1969 | 2065 | 2241 | 2078 | 2045 | 327 | 1989 | 2342 | 2051 | 1869 | 1800 | 1307 | 124 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
EVp | 0 | 927.7251 | 976.2645 | 562.7779 | 947.1495 | 1057.6352 | 2680.2521 | 324.5104 | 1795.5026 | 2169.2222 | 1860.6791 | 1397.7564 | 1285.7691 | 767.4794 | 324.7373 | 3240.3616 | 2742.9654 | 3527.0927 | 2093.3072 | 1453.7825 | 1352.5229 | 1038.7942 | 978.1119 | 1008.4908 | 1975.8426 | 1141.0801 | 510.1873 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ACp | 0 | 1605.75 | 1160.5 | 1558 | 1813.25 | 1750 | 1947.5 | 300 | 3081.75 | 1538.25 | 1901.25 | 2111.5 | 2129 | 2467.25 | 299.75 | 2987.25 | 1785.5 | 1971 | 1604.5 | 1987.75 | 1554.25 | 1556.5 | 1357.75 | 1330 | 1357 | 1445 | 1382.75 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
ESp | 0 | 0.30689 | 0.32295 | 0.18617 | 0.34131 | 0.42561 | 1.1256 | 0.13988 | 0.78763 | 1.0159 | 0.98592 | 1.6483 | 0.74038 | 0.38978 | 0.16492 | 1.5753 | 1.2538 | 2.3752 | 1.229 | 0.62074 | 0.60771 | 0.50648 | 0.49894 | 0.53959 | 1.0896 | 0.82689 | 1.2955 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
SPIc | xxx | 0.30689 | 0.34568 | 0.31512 | 0.33808 | 0.36779 | 0.51264 | 0.52632 | 0.58193 | 0.63909 | 0.66619 | 0.6619 | 0.65821 | 0.63624 | 0.64061 | 0.70925 | 0.74416 | 0.80472 | 0.8216 | 0.82092 | 0.82827 | 0.85281 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
SPI(t)c | xxx | 0.30689 | 0.31492 | 0.272 | 0.28933 | 0.31658 | 0.45142 | 0.40692 | 0.45451 | 0.51688 | 0.56379 | 0.66238 | 0.66888 | 0.64741 | 0.61295 | 0.6771 | 0.71315 | 0.81092 | 0.83414 | 0.82291 | 0.81215 | 0.7976 | 0.78402 | 0.77339 | 0.78657 | 0.78818 | 0.80769 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CPIc | xxx | 0.57775 | 0.68829 | 0.57045 | 0.55624 | 0.56692 | 0.72718 | 0.73767 | 0.70152 | 0.7754 | 0.7986 | 0.78323 | 0.76496 | 0.71703 | 0.72167 | 0.76237 | 0.81096 | 0.87439 | 0.89595 | 0.88633 | 0.88562 | 0.87647 | 0.87096 | 0.8672 | 0.88661 | 0.88332 | 0.86715 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
SPIp | xxx | 0.30689 | 0.39286 | 0.24258 | 0.41725 | 0.51342 | 1.4948 | 1.2776 | 1.0391 | 1.1017 | 0.90106 | 0.62372 | 0.61875 | 0.3753 | 0.99308 | 1.6291 | 1.1712 | 1.7197 | 1.12 | 0.80766 | 1.0348 | 8.3774 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
SPI(t)p | xxx | 0.30689 | 0.32295 | 0.18617 | 0.34131 | 0.42561 | 1.1256 | 0.13988 | 0.78763 | 1.0159 | 0.98592 | 1.6483 | 0.74038 | 0.38978 | 0.16492 | 1.5753 | 1.2538 | 2.3752 | 1.229 | 0.62074 | 0.60771 | 0.50648 | 0.49894 | 0.53959 | 1.0896 | 0.82689 | 1.2955 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CPIp | xxx | 0.57775 | 0.84124 | 0.36122 | 0.52235 | 0.60436 | 1.3763 | 1.0817 | 0.58262 | 1.4102 | 0.97866 | 0.66197 | 0.60393 | 0.31107 | 1.0834 | 1.0847 | 1.5362 | 1.7895 | 1.3046 | 0.73137 | 0.87021 | 0.66739 | 0.72039 | 0.75826 | 1.456 | 0.78967 | 0.36897 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
BAC = | 38140
PD = | 21
Z(n) @ % | 90 | xxx | 6.3138 | 2.92 | 2.3534 | 2.1318 | 2.015 | 1.9432 | 1.8946 | 1.8595 | 1.8331 | 1.8125 | 1.7959 | 1.7823 | 1.7709 | 1.7613 | 1.7531 | 1.7459 | 1.7396 | 1.7341 | 1.7291 | 1.7247 | 1.7207 | 1.7171 | 1.7139 | 1.7109 | 1.7081 | 1.7056 | 1.7033 | 1.7011 | 1.6991 | 1.6973 | 1.6955 | 1.6939 | 1.6924 | 1.6909 | 1.6896 | 1.6883 | 1.6871 | 1.686 | 1.6849 | 1.6839 | 1.6829 | 1.682 | 1.6811 | 1.6802 | 1.6794 | 1.6787 | 1.6779 | 1.6772 | 1.6766 | 1.6759 | 1.6753
Schedule
ln SPI(t)c | xxx | -1.1813 | -1.1554 | -1.302 | -1.2402 | -1.1502 | -0.79535 | -0.89915 | -0.78855 | -0.65994 | -0.57308 | -0.41192 | -0.40215 | -0.43478 | -0.48948 | -0.38993 | -0.33806 | -0.20959 | -0.18135 | -0.19491 | -0.20807 | -0.22615 | -0.24332 | -0.25697 | -0.24008 | -0.23803 | -0.21357 | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR
ln SPI(t)p | xxx | -1.1813 | -1.1303 | -1.6811 | -1.075 | -0.85424 | 0.11833 | -1.967 | -0.23873 | 0.015793 | -0.014181 | 0.49973 | -0.30059 | -0.94217 | -1.8023 | 0.45445 | 0.22621 | 0.86507 | 0.20623 | -0.47684 | -0.49806 | -0.68027 | -0.69526 | -0.61695 | 0.08578 | -0.19008 | 0.25888 | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR
Sum Ii^2 | xxx | 1.3954 | 2.6729 | 5.4991 | 6.6546 | 7.3843 | 7.3983 | 11.2674 | 11.3244 | 11.3247 | 11.3249 | 11.5746 | 11.665 | 12.5527 | 15.8008 | 16.0073 | 16.0585 | 16.8069 | 16.8494 | 17.0768 | 17.3248 | 17.7876 | 18.271 | 18.6516 | 18.659 | 18.6951 | 18.7621 | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR
- 2Ak * Sum Ii | xxx | xxx | -5.3417 | -10.3965 | -12.5697 | -13.6223 | -9.2317 | -13.9737 | -12.6313 | -10.5503 | -9.178 | -6.1853 | -6.2804 | -7.6092 | -10.3309 | -7.8754 | -6.6749 | -3.7757 | -3.1921 | -3.6166 | -4.0681 | -4.7294 | -5.4267 | -6.0482 | -5.6094 | -5.652 | -4.9608 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
k*Ak^2 | xxx | xxx | 2.6701 | 5.0852 | 6.1523 | 6.6144 | 3.7955 | 5.6593 | 4.9744 | 3.9196 | 3.2842 | 1.8665 | 1.9407 | 2.4574 | 3.3543 | 2.2807 | 1.8286 | 0.74678 | 0.59197 | 0.72177 | 0.86584 | 1.074 | 1.3025 | 1.5187 | 1.3833 | 1.4164 | 1.186 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Variation(k) | xxx | xxx | 0.0013006 | 0.18781 | 0.23727 | 0.3765 | 1.9622 | 2.953 | 3.6675 | 4.694 | 5.4311 | 7.2558 | 7.3253 | 7.4009 | 8.8242 | 10.4126 | 11.2122 | 13.778 | 14.2493 | 14.1819 | 14.1226 | 14.1323 | 14.1468 | 14.1222 | 14.4328 | 14.4595 | 14.9873 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Std Dev (s) | xxx | xxx | 0.036064 | 0.30644 | 0.28123 | 0.3068 | 0.62644 | 0.70155 | 0.72383 | 0.76599 | 0.77682 | 0.85181 | 0.81605 | 0.78533 | 0.82388 | 0.86241 | 0.86457 | 0.92797 | 0.91553 | 0.88763 | 0.86215 | 0.8406 | 0.82077 | 0.8012 | 0.79216 | 0.77619 | 0.77427 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
AFs | xxx | xxx | 0.99236 | 0.98679 | 0.97882 | 0.9689 | 0.94348 | 0.93885 | 0.91932 | 0.89338 | 0.86701 | 0.82116 | 0.79882 | 0.78631 | 0.78048 | 0.73045 | 0.68753 | 0.59778 | 0.5448 | 0.51563 | 0.48542 | 0.45869 | 0.43078 | 0.39849 | 0.32403 | 0.25317 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CLs(+) | xxx | xxx | 0.36948 | 0.45286 | 0.4 | 0.42031 | 0.73408 | 0.66007 | 0.70977 | 0.78997 | 0.83306 | 0.97076 | 0.93781 | 0.87851 | 0.83099 | 0.90172 | 0.92538 | 1.0256 | 1.0234 | 0.98726 | 0.9548 | 0.92216 | 0.89261 | 0.86706 | 0.86047 | 0.843 | 0.80769 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CLs(-) | xxx | xxx | 0.26841 | 0.16337 | 0.20928 | 0.23846 | 0.2776 | 0.25085 | 0.29105 | 0.3382 | 0.38155 | 0.45196 | 0.47707 | 0.4771 | 0.45211 | 0.50844 | 0.54959 | 0.64116 | 0.67986 | 0.68593 | 0.69082 | 0.68986 | 0.68864 | 0.68985 | 0.71901 | 0.73693 | 0.80769 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC(t)H | #N/A | #N/A | 78.2372 | 128.5424 | 100.3464 | 88.0667 | 75.6475 | 83.7149 | 72.1537 | 62.0931 | 55.0379 | 46.4645 | 44.0192 | 44.0157 | 46.4486 | 41.303 | 38.21 | 32.7533 | 30.8886 | 30.6155 | 30.3988 | 30.441 | 30.4947 | 30.4414 | 29.2067 | 28.4968 | 26 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC(t)L | #N/A | #N/A | 56.8372 | 46.3719 | 52.4997 | 49.9631 | 28.6073 | 31.8146 | 29.5871 | 26.5833 | 25.2084 | 21.6325 | 22.3925 | 23.9042 | 25.271 | 23.2888 | 22.6934 | 20.4754 | 20.5191 | 21.2711 | 21.9942 | 22.7726 | 23.5265 | 24.2199 | 24.4053 | 24.911 | 26 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC(t) | #N/A | 68.4287 | 66.6842 | 77.2059 | 72.5821 | 66.3332 | 46.5196 | 51.6077 | 46.2041 | 40.628 | 37.248 | 31.704 | 31.3959 | 32.437 | 34.2608 | 31.0145 | 29.4468 | 25.8966 | 25.1755 | 25.5191 | 25.8572 | 26.3291 | 26.785 | 27.153 | 26.6983 | 26.6436 | 26 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Cost
ln CPIc | xxx | -0.54861 | -0.37354 | -0.56133 | -0.58656 | -0.56754 | -0.31858 | -0.30425 | -0.35451 | -0.25438 | -0.22489 | -0.24433 | -0.26793 | -0.33264 | -0.32618 | -0.27133 | -0.20954 | -0.13423 | -0.10987 | -0.12067 | -0.12146 | -0.13185 | -0.13816 | -0.14249 | -0.12035 | -0.12406 | -0.14254 | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR
ln CPIp | xxx | -0.54861 | -0.17287 | -1.0183 | -0.64942 | -0.50358 | 0.31936 | 0.078535 | -0.54021 | 0.34372 | -0.02157 | -0.41253 | -0.5043 | -1.1677 | 0.080068 | 0.081332 | 0.42934 | 0.58193 | 0.26593 | -0.31283 | -0.13902 | -0.40438 | -0.32796 | -0.27672 | 0.37572 | -0.23613 | -0.99705 | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR
Sum Ii^2 | xxx | 0.30097 | 0.33086 | 1.3677 | 1.7895 | 2.0431 | 2.1451 | 2.1512 | 2.4431 | 2.5612 | 2.5617 | 2.7319 | 2.9862 | 4.3498 | 4.3562 | 4.3628 | 4.5472 | 4.8858 | 4.9565 | 5.0544 | 5.0737 | 5.2373 | 5.3448 | 5.4214 | 5.5625 | 5.6183 | 6.6124 | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR | ERR
- 2Ak * Sum Ii | xxx | xxx | -0.53901 | -1.9532 | -2.8028 | -3.2835 | -1.6397 | -1.5181 | -2.1519 | -1.3692 | -1.2202 | -1.5273 | -1.945 | -3.1916 | -3.0775 | -2.5158 | -1.763 | -0.97315 | -0.73808 | -0.88611 | -0.92572 | -1.1115 | -1.2553 | -1.3735 | -1.0697 | -1.1613 | -1.6185 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
k*Ak^2 | xxx | xxx | 0.27907 | 0.94527 | 1.3762 | 1.6105 | 0.60897 | 0.648 | 1.0054 | 0.58236 | 0.50577 | 0.65666 | 0.86142 | 1.4384 | 1.4896 | 1.1043 | 0.70251 | 0.30632 | 0.21728 | 0.27665 | 0.29506 | 0.36508 | 0.41992 | 0.46698 | 0.34761 | 0.38479 | 0.52826 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Variation(k) | xxx | xxx | 0.070917 | 0.35986 | 0.36291 | 0.37008 | 1.1144 | 1.2811 | 1.2966 | 1.7744 | 1.8472 | 1.8613 | 1.9026 | 2.5966 | 2.7683 | 2.9513 | 3.4867 | 4.219 | 4.4357 | 4.4449 | 4.4431 | 4.4908 | 4.5094 | 4.5148 | 4.8405 | 4.8418 | 5.5222 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Std Dev (c) | xxx | xxx | 0.2663 | 0.42418 | 0.34781 | 0.30417 | 0.47209 | 0.46208 | 0.43038 | 0.47095 | 0.45304 | 0.43142 | 0.41589 | 0.46517 | 0.46146 | 0.45914 | 0.48213 | 0.5135 | 0.51081 | 0.49693 | 0.48358 | 0.47386 | 0.46339 | 0.45301 | 0.45875 | 0.44916 | 0.46999 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
AFc | xxx | xxx | 0.98712 | 0.97772 | 0.96505 | 0.95077 | 0.9158 | 0.90947 | 0.88353 | 0.85098 | 0.82145 | 0.79806 | 0.77582 | 0.76182 | 0.75531 | 0.69605 | 0.64101 | 0.562 | 0.50874 | 0.46797 | 0.42654 | 0.39169 | 0.3558 | 0.31463 | 0.21235 | 0.11801 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CLc(+) | xxx | xxx | 2.2257 | 1.1478 | 0.82563 | 0.7469 | 1.0378 | 1.0044 | 0.90502 | 0.99406 | 0.99088 | 0.94537 | 0.90425 | 0.85431 | 0.85111 | 0.88162 | 0.92858 | 0.98804 | 0.99669 | 0.97224 | 0.95915 | 0.93989 | 0.92527 | 0.9126 | 0.91735 | 0.89949 | 0.86715 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CLc(-) | xxx | xxx | 0.21286 | 0.28351 | 0.37474 | 0.43031 | 0.50954 | 0.54177 | 0.54378 | 0.60484 | 0.64364 | 0.6489 | 0.64713 | 0.60181 | 0.61192 | 0.65924 | 0.70823 | 0.77381 | 0.80539 | 0.80801 | 0.81774 | 0.81734 | 0.81984 | 0.82405 | 0.8569 | 0.86745 | 0.86715 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEACH | #N/A | #N/A | 179180.97 | 134527.1444 | 101776.0846 | 88634.5608 | 74851.8793 | 70398.3325 | 70138.5961 | 63057.9616 | 59256.9765 | 58776.6981 | 58936.7167 | 63375.1812 | 62328.2211 | 57854.3609 | 53852.4483 | 49288.7763 | 47355.6739 | 47202.3052 | 46640.8367 | 46663.8181 | 46521.179 | 46283.5873 | 44509.0255 | 43968.0894 | 43983 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEACL | #N/A | #N/A | 17136.5416 | 33228.9487 | 46194.7606 | 51064.6558 | 36751.5913 | 37972.6893 | 42142.8518 | 38367.977 | 38491.1452 | 40343.8144 | 42178.8158 | 44644.2687 | 44812.2949 | 43261.1416 | 41073.3312 | 38601.7802 | 38266.6731 | 39229.0763 | 39764.5259 | 40579.4102 | 41220.3671 | 41792.626 | 41576.3368 | 42401.7679 | 43983 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC | #N/A | 66014.4929 | 55412.4729 | 66859.5213 | 68567.6444 | 67276.2465 | 52449.2676 | 51703.1334 | 54367.6417 | 49187.462 | 47758.4431 | 48695.7514 | 49858.6093 | 53191.5277 | 52849.5092 | 50028.4489 | 47030.8351 | 43619.1989 | 42569.2858 | 43031.4168 | 43065.6564 | 43515.402 | 43790.6391 | 43980.8215 | 43017.6967 | 43177.8267 | 43983 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
© Walt Lipke
MOD (S) | xxx | xxx | 0.15978 | 0.50978 | 0.32391 | 0.2834 | 0.48621 | 0.48375 | 0.44573 | 0.42418 | 0.39042 | 0.38225 | 0.33795 | 0.30525 | 0.30434 | 0.28648 | 0.26051 | 0.23489 | 0.20451 | 0.18208 | 0.16181 | 0.14512 | 0.12971 | 0.11432 | 0.0898 | 0.067241 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
MOD (C) | xxx | xxx | 1.1736 | 0.69917 | 0.39495 | 0.27571 | 0.35566 | 0.30865 | 0.2547 | 0.24842 | 0.21573 | 0.18815 | 0.16727 | 0.17517 | 0.16497 | 0.14534 | 0.13544 | 0.1222 | 0.10655 | 0.092512 | 0.079751 | 0.069854 | 0.060488 | 0.051034 | 0.03408 | 0.018137 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Stat Forecast Cost
Example Project Analysis
Final Cost Forecast Using Statistical Methods as at
2013-07-02
Period Ending | time axis 2012-12-31 to 2017-04-30
Period | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Pct [Cumulative] | 0% | 2.432% | 4.992% | 6.468% | 8.951% | 11.72% | 18.75% | 19.6% | 24.31% | 30% | 34.88% | 38.54% | 41.91% | 43.92% | 44.78% | 53.27% | 60.46% | 69.71% | 75.2% | 79.01% | 82.56% | 85.28% | 87.85% | 90.49% | 95.67% | 98.66% | 100% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Pct [Period] | 0% | 2.432% | 2.56% | 1.476% | 2.483% | 2.773% | 7.027% | 0.8508% | 4.708% | 5.688% | 4.879% | 3.665% | 3.371% | 2.012% | 0.8514% | 8.496% | 7.192% | 9.248% | 5.488% | 3.812% | 3.546% | 2.724% | 2.565% | 2.644% | 5.18% | 2.992% | 1.338% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC H | #N/A | #N/A | 179.181 | 134.5271 | 101.7761 | 88.6346 | 74.8519 | 70.3983 | 70.1386 | 63.058 | 59.257 | 58.7767 | 58.9367 | 63.3752 | 62.3282 | 57.8544 | 53.8524 | 49.2888 | 47.3557 | 47.2023 | 46.6408 | 46.6638 | 46.5212 | 46.2836 | 44.509 | 43.9681 | 43.983 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC L | #N/A | #N/A | 17.1365 | 33.2289 | 46.1948 | 51.0647 | 36.7516 | 37.9727 | 42.1429 | 38.368 | 38.4911 | 40.3438 | 42.1788 | 44.6443 | 44.8123 | 43.2611 | 41.0733 | 38.6018 | 38.2667 | 39.2291 | 39.7645 | 40.5794 | 41.2204 | 41.7926 | 41.5763 | 42.4018 | 43.983 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC CPI | #N/A | 66.0145 | 55.4125 | 66.8595 | 68.5676 | 67.2762 | 52.4493 | 51.7031 | 54.3676 | 49.1875 | 47.7584 | 48.6958 | 49.8586 | 53.1915 | 52.8495 | 50.0284 | 47.0308 | 43.6192 | 42.5693 | 43.0314 | 43.0657 | 43.5154 | 43.7906 | 43.9808 | 43.0177 | 43.1778 | 43.983 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
BAC | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14 | 38.14
Final Cost | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983 | 43.983
Std Dev (c) | xxx | xxx | 0.2663 | 0.42418 | 0.34781 | 0.30417 | 0.47209 | 0.46208 | 0.43038 | 0.47095 | 0.45304 | 0.43142 | 0.41589 | 0.46517 | 0.46146 | 0.45914 | 0.48213 | 0.5135 | 0.51081 | 0.49693 | 0.48358 | 0.47386 | 0.46339 | 0.45301 | 0.45875 | 0.44916 | 0.46999 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
© Walt Lipke
© Kym Henderson

## Stat Forecast Schedule
Example Project Analysis
Final Duration Forecast Using Statistical Methods as at
2013-07-02
Period Ending | time axis 2012-12-31 to 2017-04-30
Period | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Pct [Cumulative] | 0% | 2.432% | 4.992% | 6.468% | 8.951% | 11.72% | 18.75% | 19.6% | 24.31% | 30% | 34.88% | 38.54% | 41.91% | 43.92% | 44.78% | 53.27% | 60.46% | 69.71% | 75.2% | 79.01% | 82.56% | 85.28% | 87.85% | 90.49% | 95.67% | 98.66% | 100% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Pct [Period] | 0% | 2.432% | 2.56% | 1.476% | 2.483% | 2.773% | 7.027% | 0.8508% | 4.708% | 5.688% | 4.879% | 3.665% | 3.371% | 2.012% | 0.8514% | 8.496% | 7.192% | 9.248% | 5.488% | 3.812% | 3.546% | 2.724% | 2.565% | 2.644% | 5.18% | 2.992% | 1.338% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC(t) H | #N/A | #N/A | 78.2372 | 128.5424 | 100.3464 | 88.0667 | 75.6475 | 83.7149 | 72.1537 | 62.0931 | 55.0379 | 46.4645 | 44.0192 | 44.0157 | 46.4486 | 41.303 | 38.21 | 32.7533 | 30.8886 | 30.6155 | 30.3988 | 30.441 | 30.4947 | 30.4414 | 29.2067 | 28.4968 | 26 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC(t) L | #N/A | #N/A | 56.8372 | 46.3719 | 52.4997 | 49.9631 | 28.6073 | 31.8146 | 29.5871 | 26.5833 | 25.2084 | 21.6325 | 22.3925 | 23.9042 | 25.271 | 23.2888 | 22.6934 | 20.4754 | 20.5191 | 21.2711 | 21.9942 | 22.7726 | 23.5265 | 24.2199 | 24.4053 | 24.911 | 26 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IEAC(t) SPI(t) | #N/A | 68.4287 | 66.6842 | 77.2059 | 72.5821 | 66.3332 | 46.5196 | 51.6077 | 46.2041 | 40.628 | 37.248 | 31.704 | 31.3959 | 32.437 | 34.2608 | 31.0145 | 29.4468 | 25.8966 | 25.1755 | 25.5191 | 25.8572 | 26.3291 | 26.785 | 27.153 | 26.6983 | 26.6436 | 26 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Planned Duration | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
Final Duration | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
© Walt Lipke
© Kym Henderson

## Stat Forecast Schedule Date
Example Project Analysis
Completion Date Forecast Using Statistical Methods as at
2013-07-02
Period Ending | time axis 2012-12-31 to 2017-04-30
Period | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Pct [Cumulative] | 0% | 2.432% | 4.992% | 6.468% | 8.951% | 11.72% | 18.75% | 19.6% | 24.31% | 30% | 34.88% | 38.54% | 41.91% | 43.92% | 44.78% | 53.27% | 60.46% | 69.71% | 75.2% | 79.01% | 82.56% | 85.28% | 87.85% | 90.49% | 95.67% | 98.66% | 100% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Pct [Period] | 0% | 2.432% | 2.56% | 1.476% | 2.483% | 2.773% | 7.027% | 0.8508% | 4.708% | 5.688% | 4.879% | 3.665% | 3.371% | 2.012% | 0.8514% | 8.496% | 7.192% | 9.248% | 5.488% | 3.812% | 3.546% | 2.724% | 2.565% | 2.644% | 5.18% | 2.992% | 1.338% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IECD H | #N/A | #N/A | 2019-07-08 23:24 | 2023-09-16 06:15 | 2021-05-11 12:55 | 2020-05-02 23:45 | 2019-04-21 04:46 | 2019-12-22 14:33 | 2019-01-04 21:58 | 2018-03-04 20:55 | 2017-08-02 06:06 | 2016-11-14 10:47 | 2016-09-01 01:30 | 2016-08-31 22:59 | 2016-11-13 23:11 | 2016-06-10 10:31 | 2016-03-08 08:23 | 2015-09-24 08:33 | 2015-07-29 15:08 | 2015-07-21 07:47 | 2015-07-14 17:33 | 2015-07-16 00:23 | 2015-07-17 15:35 | 2015-07-16 00:41 | 2015-06-08 11:14 | 2015-05-17 20:55 | 2015-03-02 22:05 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IECD L | #N/A | #N/A | 2017-09-25 23:41 | 2016-11-11 15:10 | 2017-05-17 00:59 | 2017-02-28 21:05 | 2015-05-21 05:37 | 2015-08-26 19:13 | 2015-06-20 00:56 | 2015-03-20 15:54 | 2015-02-06 20:07 | 2014-10-21 01:26 | 2014-11-13 04:21 | 2014-12-29 03:58 | 2015-02-08 17:50 | 2014-12-10 10:41 | 2014-11-22 08:01 | 2014-09-15 20:39 | 2014-09-17 04:35 | 2014-10-10 01:35 | 2014-11-01 01:30 | 2014-11-24 17:49 | 2014-12-17 16:15 | 2015-01-07 18:27 | 2015-01-13 09:48 | 2015-01-28 19:01 | 2015-03-02 22:05 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
IECD SPI(t) | #N/A | 2018-09-13 14:24 | 2018-07-22 12:47 | 2019-06-07 14:29 | 2019-01-17 22:43 | 2018-07-11 20:31 | 2016-11-16 03:01 | 2017-04-19 21:45 | 2016-11-06 12:40 | 2016-05-20 21:43 | 2016-02-08 02:03 | 2015-08-23 10:26 | 2015-08-14 01:30 | 2015-09-14 17:36 | 2015-11-09 05:07 | 2015-08-02 11:03 | 2015-06-15 18:33 | 2015-02-27 18:38 | 2015-02-05 20:08 | 2015-02-16 06:59 | 2015-02-26 13:50 | 2015-03-12 22:21 | 2015-03-26 19:11 | 2015-04-06 23:54 | 2015-03-24 03:52 | 2015-03-22 11:59 | 2015-03-02 22:05 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Planned Completion Date | time axis 2014-10-01 19:41 to 2014-10-01 19:41
Actual Completion Date | time axis 2013-07-02 to 2013-07-02
© Walt Lipke
© Kym Henderson

## Percent Difference
Period | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Margin of Error Schedule | xxx | 15.98% | 50.98% | 32.39% | 28.34% | 48.62% | 48.37% | 44.57% | 42.42% | 39.04% | 38.22% | 33.79% | 30.52% | 30.43% | 28.65% | 26.05% | 23.49% | 20.45% | 18.21% | 16.18% | 14.51% | 12.97% | 11.43% | 8.98% | 6.724% | 0% |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Margin of Error Cost | xxx | 117.4% | 69.92% | 39.5% | 27.57% | 35.57% | 30.87% | 25.47% | 24.84% | 21.57% | 18.82% | 16.73% | 17.52% | 16.5% | 14.53% | 13.54% | 12.22% | 10.66% | 9.251% | 7.975% | 6.985% | 6.049% | 5.103% | 3.408% | 1.814% | 0% |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Interpretation: At |  |  | 90% | Confidence Level the nominal forecast at Period ___ is within ___% of the final duration.

## Example Data
Example using Real Data
Period | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
PV | 0 | 3023 | 5508 | 7828 | 10098 | 12158 | 13951 | 14205 | 15933 | 17902 | 19967 | 22208 | 24286 | 26331 | 26658 | 28647 | 30989 | 33040 | 34909 | 36709 | 38016 | 38140 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
EV | 0 | 927.7251 | 1903.9897 | 2466.7675 | 3413.917 | 4471.5522 | 7151.8043 | 7476.3148 | 9271.8174 | 11441.0396 | 13301.7187 | 14699.4751 | 15985.2442 | 16752.7236 | 17077.4609 | 20317.8224 | 23060.7878 | 26587.8806 | 28681.1878 | 30134.9703 | 31487.4931 | 32526.2873 | 33504.3992 | 34512.89 | 36488.7326 | 37629.8127 | 38140 | #N/A
AC | 0 | 1605.75 | 2766.25 | 4324.25 | 6137.5 | 7887.5 | 9835 | 10135 | 13216.75 | 14755 | 16656.25 | 18767.75 | 20896.75 | 23364 | 23663.75 | 26651 | 28436.5 | 30407.5 | 32012 | 33999.75 | 35554 | 37110.5 | 38468.25 | 39798.25 | 41155.25 | 42600.25 | 43983 | #N/A
PV | 0 | 93 | 644 | 975 | 1275 | 1739 | 2292 | 3331 | 3869 | 4612 | 5527 | 6575 | 7991 | 9193 | 10831 | 12946 | 14295 | 16051 | 17808 | 19666 | 21178 | 22839 | 24873 | 26310 | 27720 | 29113 | 30298 | 31821
EV | 0 | 93 | 644 | 1710 | 2397 | 3060 | 3923 | 4722 | 5743 | 7369 | 9005 | 10850 | 12218 | 13921 | 15417 | 18170 | 20022 | 21936 | 24418 | 26186 | 27972 | 29397 | 30899 | 31821 | #N/A | #N/A | #N/A | #N/A
AC | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A