## Instruction Notes
Notes - Planning Calculator Probability & Reserves
1. The Reserves & Probability Calculator stands alone with its own set of instructions. The instruction for use
is on the "Reserv & Prob Calculator" sheet.
2. The standard deviation (s) expected in the "Reserv & Prob Calculator" sheet comes from the variation of the
periodic values of ln CPI and ln SPI(t) from the logarithm of their respective cumulative values. The expectation
is that s will be available for planning from a similar historical project or from a qualitative assessment of
risk for the new project. If history data is available (EV, AC, ES, AT) and is to be used for planning but the
standard deviation (s) has not been recorded in the project archives, it may be calculated using the Standard
Deviation Calculator. The calculator sheet is "Std Dev Calculator" which has a set of instructions on the sheet
named "Instr Std Dev Calc." When the standard deviation calculator is used, the last value in column J is the
standard deviation value to be be entered to the "Reserv & Prob Calculator" sheet.

## Reserv & Prob Calculator
Cost |  | Schedule
Budget at Completion | 1000 | Planned Duration | 30
Reserve (cost) | 100 | Reserve (schedule) | 5
Total Allocated Budget | 1100 | Total Duration | 35
Cost Ratio | 1.1 | Schedule Ratio | 1.1667
s(cost history) | 0.5 | s(schedule history) | 0.8
n (observations) | 5
Student-t (cost) | 0.42624 | Student-t (schedule) | 0.43086
Probability (cost) | 65.41% | Probability (schedule) | 65.56%
Planning Calculator Instructions - Probability & Reserves
Cost |  | Schedule
1. Enter values for BAC, cost reserve and the planned |  | 1. Enter values for planned duration, schedule reserve and
number of observations (n) for the new project. |  | the planned number of observations (n) for the new project.
2. Enter value for standard deviation for cost (s) from |  | 2. Enter value for standard deviation for schedule (s) from
historical project. If history is not available select value |  | historical project. If history is not available select value
from Risk - Standard Deviation table below. |  | from Risk - Standard Deviation table below.
3. Adjust value of cost reserve to obtain desired probability |  | 3. Adjust value of schedule reserve to obtain desired
of success. |  | probability of success.
Note: the Risk - Standard Deviation table below contains
values associated with status taken monthly. When weekly
status is used, multiply the table values by 2.
Risk - Standard Deviation
| Very Low | 0.000 - 0.150
| Low | 0.200 - 0.350
| Medium | 0.400 - 0.600
| High | 0.650 - 0.950
| Very High | 1.000 - Infinity

## Plnng Calc Example Data
Planning Calculator - Example Data
Cost |  | Schedule
Budget at Completion | 1000 | Planned Duration | 30
Reserve (cost) | 300 | Reserve (schedule) | 7
s(cost history) | 0.85 | s(schedule history) | 0.65
n (observations) | 30
Example Data Calculated Results
Cost |  | Schedule
Cost Ratio | 1.3 | Schedule Ratio | 1.2333
Student-t (cost) | 1.6906 | Student-t (schedule) | 1.7672
Probability (cost) | 94.92% | Probability (schedule) | 95.61%

## Instr Std Dev Calc
Instruction - Standard Deviation Calculator
The Standard Deviation Calculator is very easy to use. All that is required is to enter the cumulative and
periodic performance indicator values into the appropriate blue colored columns. For periods where data is
unavailable, the input cells must be left blank. Upon entry, the calculation of the standard deviation is then
performed, with the results displayed in the gray colored column at the right of the spreadsheet. The last
calculated value displayed in the Std Dev (k) column is to be entered to the Reserv & Prob Calculator.
This calculator is specifically for CPI and SPI(t). The calculation is different from the normal method. Instead of
using the calculated average, the deviation is determined from the cumulative indicator value. The standard
deviation result represents the variation in the values of the natural logarithms values of the indexes. The
distribution of the natural logarithms values can be assumed to be normal.
It is to be noted that when a periodic entry is negative, indicating a retroactive downward change to EV value
claimed, a negative value occurs for xPIp. When this occurs, no calculated value for the standard deviation can
be made. The Std Dev (k) column will show "Std Dev (k)" just as when input cells are left blank.

## Std Dev Calculator
Standard Deviation Calculator
Period | xPIc | xPIp | ln xPIc | ln xPIp | Sum Ii^2 | - 2Ak * Sum Ii | k*Ak^2 | Variation(k) | Std Dev (k)
1 |  |  | ln xPIc | ln xPIp | xxx | xxx | xxx | xxx | xxx
2 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
3 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
4 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
5 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
6 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
7 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
8 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
9 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
10 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
11 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
12 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
13 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
14 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
15 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
16 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
17 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
18 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
19 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
20 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
21 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
22 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
23 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
24 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
25 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
26 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
27 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
28 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
29 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
30 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
31 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
32 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
33 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
34 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
35 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
36 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
37 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
38 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
39 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
40 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
41 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
42 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
43 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
44 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
45 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
46 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
47 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
48 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
49 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
50 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
51 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
52 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
53 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
54 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
55 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
56 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
57 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
58 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
59 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)
60 |  |  | ln xPIc | ln xPIp | SumIi^2 | - 2Ak * SumIi | k*Ak^2 | Variation(k) | Std Dev (k)